## query (14)
Title | Project | Task | POC | Mailto | POC Email | Organization | Start Date | End Date | Public Meeting | Due to Commission | Internal Deliverable | Deadline in the ADVANCE Act | Status
101. International nuclear export and innovation activities. | International Nuclear Export and Innovation | Identify international nuclear export and innovation activities in the annual budget justification starting with FY 2026 | Jennifer Holzman | mailto:jennifer.holzman@nrc.gov | Jennifer.Holzman@nrc.gov | OIP | 2024-07-09 | 2025-04-30 |  |  | 2025-04-30 |  | Complete
102. Denial of certain domestic licenses for national security purposes. | International Nuclear Export and Innovation | Inform external stakeholders about section 102 and develop procedures to consult with DOE and State Department prior to the NRC issuing a license to possess or own “covered fuel” and to provide notification to Congress | Bo Pham | mailto:bo.pham@nrc.gov | Bo.Pham@nrc.gov | NRR | 2024-07-09 | 2025-06-30 |  |  | 2025-06-30 |  | In Progress
103. Export license notification. | International Nuclear Export and Innovation | Develop procedures to inform the Commission and to notify Congress when certain export licenses are issued to countries that meet specific criteria | Jennifer Holzman | mailto:jennifer.holzman@nrc.gov | Jennifer.Holzman@nrc.gov | OIP | 2024-07-09 | 2025-10-01 |  |  | 2025-10-01 |  | In Progress
201. Fees for advanced nuclear reactor application review. | Reduced Hourly Rate and Exclusion of Additional Activities | Establish a reduced hourly rate for advanced nuclear reactor applicants and pre-applicants for certain activities effective FY 2026 | Julio Areas | mailto:julio.areas@nrc.gov | Julio.Areas@nrc.gov | OCFO | 2024-07-09 | 2025-10-01 |  |  | 2024-12-13 | 2025-10-01 | In Progress
201. Fees for advanced nuclear reactor application review. | Reduced Hourly Rate and Exclusion of Additional Activities | Establish process for implementing reduced hourly fees per Section 201 of the ADVANCE Act, including clarifying entrance and exit criteria and scope | Tanya Smith | mailto:Tanya.Smith@nrc.gov | Tanya.Smith@nrc.gov | NRR | 2025-01-31 | 2025-06-30 |  |  | 2025-06-30 |  | In Progress
203. Licensing considerations relating to use of nuclear energy for nonelectric applications | Non-Electric Uses of Nuclear Energy | Submit a report to Congress on non-electric uses of nuclear energy | William Reckley | mailto:william.reckley@nrc.gov | William.Reckley@nrc.gov | NRR | 2024-07-09 | 2025-04-25 | 2024-12-12 | 2025-03-24 |  | 2025-04-25 | In Progress
204. Enabling preparations for the demonstration of advanced nuclear reactors on Department of Energy sites or critical national security infrastructure sites. | Reduced Hourly Rate and Exclusion of Additional Activities | Incorporate in the FY 2026 fee rule the exclusion of additional activities from the fee-recovery requirement | Julio Areas | mailto:julio.areas@nrc.gov | Julio.Areas@nrc.gov | OCFO | 2024-07-09 | 2025-10-01 |  |  | 2024-12-13 | 2025-10-01 | In Progress
205. Fusion energy regulation. | Fusion Licensing Framework Report | Submit a report to Congress on licensing frameworks for mass-manufactured fusion machines | Kevin Williams | mailto:kevin.williams@nrc.gov | Kevin.Williams@nrc.gov | NMSS | 2024-07-09 | 2025-07-09 | 2025-03-05 | 2025-06-23 |  | 2025-07-09 | In Progress
206. Regulatory issues for nuclear facilities at brownfield sites. | Brownfield Site Facilities | Assess potential regulatory modifications to achieve efficient, timely, and predictable licensing reviews for and oversight of nuclear facilities at brownfield sites and retired fossil fuel sites | Sarah Lopas | mailto:sarah.lopas@nrc.gov | Sarah.Lopas@nrc.gov | NMSS | 2024-07-09 | 2025-07-09 | 2025-03-06 |  |  | 2025-07-09 | In Progress
206. Regulatory issues for nuclear facilities at brownfield sites. | Brownfield Site Facilities | Submit a report to Congress on potential regulatory modifications for nuclear facilities at brownfield sites and retired fossil fuel sites | Sarah Lopas | mailto:sarah.lopas@nrc.gov | Sarah.Lopas@nrc.gov | NMSS | 2024-07-09 | 2025-09-09 | 2025-01-16 | 2025-08-25 |  | 2025-09-09 | In Progress
206. Regulatory issues for nuclear facilities at brownfield sites. | Brownfield Site Facilities | Develop and implement strategies to achieve efficient, timely, and predictable licensing reviews for and oversight of nuclear facilities at brownfield sites and retired fossil fuel sites | Sarah Lopas | mailto:sarah.lopas@nrc.gov | Sarah.Lopas@nrc.gov | NMSS | 2024-07-09 | 2026-07-09 | 2025-01-16 |  |  | 2026-07-09 | In Progress
206. Regulatory issues for nuclear facilities at brownfield sites. | Brownfield Site Facilities | Submit a report to Congress on implementation of strategies for nuclear facilities at brownfield sites and retired fossil fuel sites | Sarah Lopas | mailto:sarah.lopas@nrc.gov | Sarah.Lopas@nrc.gov | NMSS | 2024-07-09 | 2027-07-09 | 2025-01-16 | 2027-06-24 |  | 2027-07-09 | In Progress
207. Combined license review procedure. | Expedited Procedures for Combined Licenses | Establish an expedited procedure for the review of qualifying combined license applications | Samuel Lee | mailto:samuel.lee@nrc.gov | Samuel.Lee@nrc.gov | NRR | 2024-07-09 | 2025-09-09 | 2025-03-04 |  | 2025-09-09 |  | In Progress
208. Regulatory requirements for micro-reactors. | Streamlining Reviews for Micro-Reactors | Develop risk-informed and performance-based strategies and guidance for the licensing and regulation of micro-reactors | William Kennedy | mailto:william.kennedy@nrc.gov | William.Kennedy@nrc.gov | NRR | 2024-07-09 | 2026-01-09 | 2025-04-21 |  |  | 2026-01-09 | In Progress
208. Regulatory requirements for micro-reactors. | Streamlining Reviews for Micro-Reactors | Implement risk-informed and performance-based strategies and guidance for the licensing and regulation of micro-reactors | William Kennedy | mailto:william.kennedy@nrc.gov | William.Kennedy@nrc.gov | NRR | 2024-07-09 | 2027-07-09 | 2025-04-21 |  |  | 2027-07-09 | In Progress
301. Foreign ownership. | Foreign Ownership | Implement actions to address any identified impacts of section 301 | Shawn Harwell | mailto:shawn.harwell@nrc.gov | Shawn.Harwell@nrc.gov | NMSS | 2024-07-09 | 2025-03-31 |  |  | 2025-03-31 |  | Complete
401. Report on advanced methods of manufacturing and construction for nuclear energy projects. | Manufacturing and Construction for Nuclear Energy Projects | Submit a report to Congress on advanced methods of manufacturing and construction for nuclear energy projects | Angie Buford | mailto:angela.buford@nrc.gov | Angela.Buford@nrc.gov | NRR | 2024-07-09 | 2025-01-05 | 2024-10-30 | 2024-12-13 |  | 2025-01-05 | Complete
402. Nuclear energy traineeship. | Nuclear Energy Traineeship Sub-program | Establish a nuclear energy traineeship subprogram as part of the University Nuclear Leadership Program | Michael Brezovec | mailto:michael.brezovec@nrc.gov | Michael.Brezovec@nrc.gov | RES | 2024-07-09 | 2025-07-31 | 2025-02-27 | 2025-07-31 |  |  | In Progress
404. Development, qualification, and licensing of advanced nuclear fuel concepts. | Advanced Nuclear Fuel MOU with DOE | Develop a memorandum of understanding with DOE focused on advanced nuclear fuel | James Delosreyes | mailto:james.delosreyes@nrc.gov | James.Delosreyes@nrc.gov | NRR | 2024-07-09 | 2025-01-05 |  |  |  | 2025-01-05 | Complete
404. Development, qualification, and licensing of advanced nuclear fuel concepts. | Advanced Nuclear Fuel Qualification and Licensing | Submit a report to Congress on implementation of an initiative to enhance preparedness and coordination with respect to the qualification and licensing of advanced nuclear fuel | James Delosreyes | mailto:james.delosreyes@nrc.gov | James.Delosreyes@nrc.gov | NRR | 2024-07-09 | 2026-07-09 |  | 2026-06-23 |  | 2026-07-09 | In Progress
501. Mission alignment. | NRC Mission Statement | Provide recommendations for mission statement update | Julie Ezell | mailto:julie.ezell@nrc.gov | Julie.Ezell@nrc.gov | OGC | 2024-07-09 | 2024-10-08 |  |  | 2024-10-08 |  | Complete
501. Mission alignment. | NRC Mission Statement | Provide recommendations for implementing guidance | Sabrina Atack | mailto:sabrina.atack@nrc.gov | Sabrina.Atack@nrc.gov | OEDO | 2024-07-09 | 2025-05-02 |  | 2025-05-02 |  |  | In Progress
501. Mission alignment. | NRC Mission Statement | Update the NRC mission statement within one year, and thereafter submit a report to Congress on updated mission statement and implementing guidance | Sabrina Atack | mailto:sabrina.atack@nrc.gov | Sabrina.Atack@nrc.gov | OEDO | 2024-07-09 | 2025-07-09 |  |  |  | 2025-07-09 | In Progress
502. Strengthening the NRC workforce. | Annual NRAN Solicitation | Solicit applications for the Nuclear Regulator Apprenticeship Network (NRAN) annually | Susan Abraham | mailto:susan.abraham@nrc.gov | Susan.Abraham@nrc.gov | OCHCO | 2024-07-09 | 2025-01-31 |  |  | 2025-01-31 |  | Complete
502. Strengthening the NRC workforce. | Special Compensation | Include hiring, vacancies, and compensation Information in the annual budget justification starting with FY 2026 | Rich Revzan | mailto:richard.revzan@nrc.gov | Richard.Revzan@nrc.gov | OCHCO | 2024-07-09 | 2025-04-30 |  |  |  | 2025-02-07 | In Progress
502. Strengthening the NRC workforce. | Special Compensation | Submit a report to Congress and OPM on plan to implement special compensation authority | Rich Revzan | mailto:richard.revzan@nrc.gov | Richard.Revzan@nrc.gov | OCHCO | 2024-07-09 | 2025-01-05 |  | 2024-12-06 |  | 2025-01-05 | Complete
503. Commission corporate support funding. | Other Corporate Support Cap Changes | Implement other corporate support cap changes | Julio Areas | mailto:julio.areas@nrc.gov | Julio.Areas@nrc.gov | OCFO | 2024-07-09 | 2025-04-30 |  |  | 2025-04-30 |  | In Progress
503. Commission corporate support funding. | NEIMA Corporate Support Cap Report | Submit a report to Congress on NEIMA corporate support cap | Julio Areas | mailto:julio.areas@nrc.gov | Julio.Areas@nrc.gov | OCFO | 2024-07-09 | 2027-07-09 |  |  |  | 2027-07-09 | In Progress
504. Performance metrics and milestones. | NEIMA Milestone Schedules | Review every 3 years and revise and improve metrics and milestones, as needed | Caroline Carusone | mailto:caroline.carusone@nrc.gov | Caroline.Carusone@nrc.gov | OCIO | 2024-07-09 | 2025-04-25 |  | 2025-04-25 |  |  | In Progress
504. Performance metrics and milestones. | NEIMA Reporting Change to 90 Days | Update procedures to reflect NEIMA reporting change to 90 days for requested activities of the Commission | Mike King | mailto:mike.king@nrc.gov | Mike.King@nrc.gov | All Offices | 2024-07-09 | 2024-09-23 |  |  | 2024-09-23 |  | Complete
505. Nuclear licensing efficiency. | Techniques and Guidance for Nuclear Reactor License Application Reviews | Establish techniques and guidance to support efficient, timely, and predictable reviews of nuclear reactor license applications and periodically evaluate for potential modifications | Jamie Pelton | mailto:jamieheisserer@nrc.gov | Jamie.Heisserer@nrc.gov | NRR | 2024-07-09 | 2025-07-09 | 2025-04-10 |  | 2025-07-09 |  | In Progress
506. Modernization of nuclear reactor environmental reviews. | Nuclear Reactor Environmental Reviews | Submit a report to Congress on efforts to facilitate efficient, timely, and predictable environmental reviews for nuclear reactor license applications | Ted Smith | mailto:theodore.smith@nrc.gov | Theodore.Smith@nrc.gov | NMSS | 2024-07-09 | 2025-01-05 |  | 2024-12-13 |  | 2025-01-05 | Complete
507. Improving oversight and inspection programs. | Oversight and Inspection Programs | Submit a report to Congress on improvements to oversight and inspection programs | Philip McKenna | mailto:philip.mckenna@nrc.gov | Philip.McKenna@nrc.gov | NRR | 2024-07-09 | 2025-07-09 | 2025-02-19 | 2025-06-13 |  | 2025-07-09 | In Progress
601. Technical correction. | NPUF Criteria | Develop revised rulemaking plan on cost criteria for non-power utilization facilities | Holly Cruz | mailto:holly.cruz@nrc.gov | Holly.Cruz@nrc.gov | NRR | 2024-07-09 | 2025-03-24 |  |  | 2025-03-24 |  | Complete
601. Technical correction. | NPUF Criteria | Withdraw rulemaking plan on cost recovery criteria for non-power utilization facilities | Holly Cruz | mailto:holly.cruz@nrc.gov | Holly.Cruz@nrc.gov | NRR | 2024-07-09 | 2024-10-10 |  |  | 2024-10-10 |  | Complete
602. Report on engagement with the Government of Canada with respect to nuclear waste issues in the Great Lakes Basin. | Great Lakes Basin Nuclear Waste Issues | Submit a report to Congress on engagement with Canada relating to nuclear waste issues in the Great Lakes Basin | Shawn Smith | mailto:shawn.smith@nrc.gov | Shawn.Smith@nrc.gov | NMSS | 2024-07-09 | 2025-07-09 |  |  | 2025-06-30 | 2025-07-09 | In Progress