## Subsequent License Renewal
Title | Milestone | Review Status | Duration Type | Hours | Start Date | End Date | Sort Column
Turkey Point Nuclear Plant, Units 3 and 4 | Estimated License Review | Complete | Planned | 24000 | 2018-04-26 | 2024-09-17 | 1
Turkey Point Nuclear Plant, Units 3 and 4 | Safety Review | Complete | Actual | 18731 | 2018-04-26 | 2019-07-22 | 3
Turkey Point Nuclear Plant, Units 3 and 4 | Environmental Review | Complete | Actual | 16105 | 2018-04-26 | 2024-03-29 | 4
Turkey Point Nuclear Plant, Units 3 and 4 | Overall License Review | Complete | Actual | 34836 | 2018-04-26 | 2024-09-17 | 2
Peach Bottom Atomic Power Station, Units 2 and 3 | Estimated License Review | Ongoing | Planned | 21000 | 2018-08-27 | 2026-02-28 | 6
Peach Bottom Atomic Power Station, Units 2 and 3 | Overall License Review | Ongoing | Actual | 21989 | 2018-08-27 | 2026-02-28 | 7
Peach Bottom Atomic Power Station, Units 2 and 3 | Safety Review | Complete | Actual | 15735 | 2018-08-27 | 2019-11-19 | 8
Peach Bottom Atomic Power Station, Units 2 and 3 | Environmental Review | Ongoing | Actual | 6254 | 2018-08-27 | 2025-12-31 | 9
Surry Power Station, Units 1 and 2 | Estimated License Review | Complete | Planned | 21000 | 2018-12-03 | 2021-05-31 | 11
Surry Power Station, Units 1 and 2 | Overall License Review | Complete | Actual | 22908 | 2018-12-03 | 2021-05-04 | 12
Surry Power Station, Units 1 and 2 | Safety Review | Complete | Actual | 18007 | 2018-12-03 | 2020-03-09 | 13
Surry Power Station, Units 1 and 2 | Environmental Review | Complete | Actual | 6963 | 2018-12-03 | 2020-04-06 | 14
North Anna Power Station, Units 1 and 2 | Estimated License Review | Complete | Planned | 23000 | 2020-10-13 | 2024-08-30 | 15
North Anna Power Station, Units 1 and 2 | Overall License Review | Complete | Actual | 20866 | 2020-10-13 | 2024-08-28 | 16
North Anna Power Station, Units 1 and 2 | Safety Review | Complete | Actual | 10979 | 2020-10-13 | 2022-01-04 | 17
North Anna Power Station, Units 1 and 2 | Environmental Review | Complete | Actual | 9887 | 2020-10-13 | 2022-02-24 | 18
Point Beach Nuclear Plant, Units 1 and 2 | Estimated License Review | Ongoing | Planned | 23000 | 2021-01-15 | 2025-12-31 | 20
Point Beach Nuclear Plant, Units 1 and 2 | Overall License Review | Ongoing | Actual | 18070 | 2021-01-15 | 2025-12-31 | 21
Point Beach Nuclear Plant, Units 1 and 2 | Safety Review | Complete | Actual | 12425 | 2021-01-15 | 2022-02-23 | 22
Point Beach Nuclear Plant, Units 1 and 2 | Environmental Review | Ongoing | Actual | 5645 | 2021-01-15 | 2025-10-31 | 23
Oconee Nuclear Station, Units 1, 2, and 3 | Estimated License Review | Complete | Planned | 23000 | 2021-07-22 | 2025-03-31 | 25
Oconee Nuclear Station, Units 1, 2, and 3 | Overall License Review | Complete | Actual | 20425 | 2021-07-22 | 2025-03-31 | 26
Oconee Nuclear Station, Units 1, 2, and 3 | Safety Review | Complete | Actual | 13392 | 2021-07-22 | 2022-12-19 | 27
Oconee Nuclear Station, Units 1, 2, and 3 | Environmental Review | Complete | Actual | 7033 | 2021-07-22 | 2025-01-31 | 28
St. Lucie Nuclear Plant, Units 1 and 2 | Estimated License Review | Ongoing | Planned | 21000 | 2021-09-29 | 2026-09-30 | 30
St. Lucie Nuclear Plant, Units 1 and 2 | Overall License Review | Ongoing | Actual | 16468 | 2021-09-29 | 2026-09-30 | 31
St. Lucie Nuclear Plant, Units 1 and 2 | Safety Review | Complete | Actual | 14436 | 2021-09-29 | 2023-07-21 | 32
St. Lucie Nuclear Plant, Units 1 and 2 | Environmental Review | Ongoing | Actual | 2032 | 2021-09-29 | 2026-07-31 | 33
Monticello Nuclear Generating Plant, Unit 1 | Estimated License Review | Complete | Planned | 24000 | 2023-02-23 | 2024-12-30 | 35
Monticello Nuclear Generating Plant, Unit 1 | Overall License Review | Complete | Actual | 16206 | 2023-02-23 | 2024-12-30 | 36
Monticello Nuclear Generating Plant, Unit 1 | Safety Review | Complete | Actual | 8260 | 2023-02-23 | 2024-03-18 | 37
Monticello Nuclear Generating Plant, Unit 1 | Environmental Review | Complete | Actual | 7946 | 2023-02-23 | 2024-11-15 | 38
Virgil C. Summer Nuclear Station, Unit 1 | Estimated License Review | Ongoing | Planned | 20000 | 2023-10-11 | 2025-08-30 | 39
Virgil C. Summer Nuclear Station, Unit 1 | Overall License Review | Ongoing | Actual | 11661 | 2023-10-11 | 2025-06-30 | 40
Virgil C. Summer Nuclear Station, Unit 1 | Safety Review | Complete | Actual | 7896 | 2023-10-11 | 2025-01-21 | 41
Virgil C. Summer Nuclear Station, Unit 1 | Environmental Review | Ongoing | Actual | 3765 | 2023-10-11 | 2025-05-08 | 42
Browns Ferry Nuclear Plant, Units 1, 2, and 3 | Estimated License Review | Ongoing | Planned | 19000 | 2024-03-15 | 2026-01-31 | 43
Browns Ferry Nuclear Plant, Units 1, 2, and 3 | Overall License Review | Ongoing | Actual | 13457 | 2024-03-15 | 2026-01-31 | 44
Browns Ferry Nuclear Plant, Units 1, 2, and 3 | Safety Review | Ongoing | Actual | 9127 | 2024-03-15 | 2025-07-30 | 45
Browns Ferry Nuclear Plant, Units 1, 2, and 3 | Environmental Review | Ongoing | Actual | 4330 | 2024-03-15 | 2025-11-30 | 46
Dresden Nuclear Power Station, Units 2 and 3 | Estimated License Review | Ongoing | Planned | 14000 | 2024-06-14 | 2025-12-30 | 47
Dresden Nuclear Power Station, Units 2 and 3 | Overall License Review | Ongoing | Actual | 9808 | 2024-06-14 | 2025-12-30 | 48
Dresden Nuclear Power Station, Units 2 and 3 | Safety Review | Ongoing | Actual | 6039 | 2024-06-14 | 2025-09-30 | 49
Dresden Nuclear Power Station, Units 2 and 3 | Environmental Review | Ongoing | Actual | 3769 | 2024-06-14 | 2025-10-30 | 50
H.B. Robinson Steam Electric Plant, Unit 2 | Estimated License Review | Ongoing | Planned | 12800 | 2025-04-28 | 2026-04-28 | 51
H.B. Robinson Steam Electric Plant, Unit 2 | Overall License Review | Ongoing | Actual | 495 | 2025-04-28 | 2026-04-28 | 52
H.B. Robinson Steam Electric Plant, Unit 2 | Safety Review | Ongoing | Actual | 276 | 2025-04-28 | 2026-04-28 | 53
H.B. Robinson Steam Electric Plant, Unit 2 | Environmental Review | Ongoing | Actual | 219 | 2025-04-28 | 2026-04-28 | 54
Edwin I. Hatch Nuclear Power Plant, Units 1 and 2 | Estimated License Review | Ongoing | Planned |  | 2025-06-13 | 2026-06-13 | 55
Edwin I. Hatch Nuclear Power Plant, Units 1 and 2 | Overall License Review | Ongoing | Actual |  | 2025-06-13 | 2026-06-13 | 56
Edwin I. Hatch Nuclear Power Plant, Units 1 and 2 | Safety Review | Ongoing | Actual |  | 2025-06-13 | 2026-05-31 | 57
Edwin I. Hatch Nuclear Power Plant, Units 1 and 2 | Environmental Review | Ongoing | Actual |  | 2025-06-13 | 2026-03-31 | 58
Turkey Point Nuclear Plant, Units 3 and 4 | Environmental Review Pause | Paused | Actual |  | 2019-10-25 | 2022-06-09 | 5
Peach Bottom Atomic Power Station, Units 2 and 3 | Environmental Review Pause | Paused | Actual |  | 2020-01-27 | 2024-09-06 | 10
North Anna Power Station, Units 1 and 2 | Environmental Review Pause | Paused | Actual |  | 2022-02-24 | 2022-09-28 | 19
Point Beach Nuclear Plant, Units 1 and 2 | Environmental Review Pause | Paused | Actual |  | 2022-02-24 | 2024-09-30 | 24
Oconee Nuclear Station, Units 1, 2, and 3 | Environmental Review Pause | Paused | Actual |  | 2022-02-24 | 2022-11-07 | 29
St. Lucie Nuclear Plant, Units 1 and 2 | Environmental Review Pause | Paused | Actual |  | 2022-02-24 | 2024-10-18 | 34

## License Renewal
Title | Status | Milestone | Review | Hours | Start Date | End Date | Sort Column
Comanche Peak Nuclear Power Plant, Units 1 and 2 | Complete | Estimated Overall License Review | Planned Hours | 23000 | 2022-11-29 | 2024-09-30 | 1
Comanche Peak Nuclear Power Plant, Units 1 and 2 | Complete | Overall License Review | Total Hours | 17147 | 2022-11-29 | 2024-07-30 | 2
Comanche Peak Nuclear Power Plant, Units 1 and 2 | Complete | Safety Review | Safety Review Hours | 10423 | 2022-11-29 | 2024-03-18 | 3
Comanche Peak Nuclear Power Plant, Units 1 and 2 | Complete | Environmental Review | Environmental Review Hours | 6724 | 2022-11-29 | 2024-04-26 | 4
Perry Nuclear Power Plant, Unit 1 | Ongoing | Estimated Overall License Review | Planned Hours | 20000 | 2023-09-29 | 2025-07-31 | 5
Perry Nuclear Power Plant, Unit 1 | Ongoing | Overall License Review | Total Hours | 16785 | 2023-09-29 | 2025-07-07 | 6
Perry Nuclear Power Plant, Unit 1 | Ongoing | Safety Review | Safety Review Hours | 11664 | 2023-09-29 | 2025-05-29 | 7
Perry Nuclear Power Plant, Unit 1 | Ongoing | Environmental Review | Environmental Review Hours | 5121 | 2023-09-29 | 2025-04-30 | 8
Diablo Canyon Power Plant, Units 1 and 2 | Ongoing | Estimated Overall License Review | Planned Hours | 16500 | 2023-12-19 | 2025-08-31 | 9
Diablo Canyon Power Plant, Units 1 and 2 | Ongoing | Overall License Review | Total Hours | 13617 | 2023-12-19 | 2025-08-31 | 10
Diablo Canyon Power Plant, Units 1 and 2 | Ongoing | Safety Review | Safety Review Hours | 7854 | 2023-12-19 | 2025-06-05 | 11
Diablo Canyon Power Plant, Units 1 and 2 | Ongoing | Environmental Review | Environmental Review Hours | 5763 | 2023-12-19 | 2025-06-20 | 12
Clinton Power Station, Unit 1 | Complete | Estimated Overall License Review | Planned Hours | 17000 | 2024-04-18 | 2025-12-31 | 13
Clinton Power Station, Unit 1 | Complete | Overall License Review | Total Hours | 10840 | 2024-04-18 | 2025-12-31 | 14
Clinton Power Station, Unit 1 | Complete | Safety Review | Safety Review Hours | 6149 | 2024-04-18 | 2025-08-31 | 15
Clinton Power Station, Unit 1 | Complete | Environmental Review | Environmental Review Hours | 4691 | 2024-04-18 | 2025-10-31 | 16