## CFPP Exemption Milestones
Review | Milestone | Start | End
CFPP Exemption Request | CFPP Exemption Request | 2023-07-31 | 2023-12-20
CFPP Exemption Request | 1 - NRC Document Processing, SUNSI, Kickoff Meeting | 2023-07-31 | 2023-08-09
CFPP Exemption Request | 2 - NRC Acceptance Review Completed | 2023-08-09 | 2023-08-31
CFPP Exemption Request | 3 - RAIs Issued | 2023-09-01 | 2023-09-29
CFPP Exemption Request | 4 - RAI Responses from CFPP | 2023-09-30 | 2023-11-03
CFPP Exemption Request | 5 - Draft SER Sent to OGC | 2023-11-04 | 2024-03-01
CFPP Exemption Request | 6 - OGC Response | 2024-03-01 | 2024-03-21
CFPP Exemption Request | 7 - NRC Issues FSER | 2024-03-21 | 2024-12-20
CFPP Exemption Request | 8 - NRC Issues FONSI | 2024-09-21 | 2024-12-20
CFPP Exemption Request | 9 - Tentative: Exemption Approval | 2024-12-20 | 2024-12-27

## CFPP Exemption RAIs
Chapter/Section | Regulatory Basis | Issue | Status | Date Resolved | RAI #
0 | 0 | 0 | 0 | 0 | 0

## CFPP LWA Milestones
Review | Milestone | Start | End
LWA Review | LWA Review | 2023-07-31 | 2025-08-06
LWA Review | 1 - NRC Document Processing, SUNSI, Kickoff Meeting | 2023-07-31 | 2023-08-09
LWA Review | 2 - NRC Acceptance Review | 2023-08-09 | 2023-08-31
LWA Review | 3 - NRC Publication of NOI for DEIS/FRN | #REF! | 2025-08-22
LWA Review | 4 - Audit and Issue RAIs | 2023-09-27 | 2024-01-27
LWA Review | 5 - RAI Responses from CFPP | 2024-01-27 | 2024-03-27
LWA Review | 6 - NRC Issues DEIS/Advanced SE | 2023-09-27 | 2024-07-11
LWA Review | 7 - NRC Issues FEIS/ACRS Complete | 2024-07-11 | 2025-03-05
LWA Review | 8 - NRC Issues EIS ROD/FSER Complete | 2025-03-05 | 2025-04-04
LWA Review | 9 - ASLB Hearing/Initial Decision | 2025-04-04 | 2025-08-05
LWA Review | Tentative: NRC Approval of LWA | 2025-08-05 | 2025-08-22

## CFPP LWA RAIs
Chapter/Section | Regulatory Basis | Issue | Status | Date Resolved | RAI #
0 | 0 | 0 | 0 | 0 | 0