## Strategy
Commission Papers | Guidance | Rulemaking | NEIMA | Complete | Strategy | Activity Level | Regulatory Activity | Main Activity | Sub-Activity 1 | Sub-Activity 2 | Sub-Activity 3
|  |  |  | x | 1 | 1.1 | Development of non-Light Water Reactor (LWR) Training for Advanced Reactors (Adv. Rxs) (NEIMA Section 103(a)(5)) | Development of non-Light Water Reactor (LWR) Training for Advanced Reactors (Adv. Rxs) (NEIMA Section 103(a)(5)) | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | 1 | 1.1.1 | FAST Reactor Technology | Development of non-Light Water Reactor (LWR) Training for Advanced Reactors (Adv. Rxs) (NEIMA Section 103(a)(5)) | FAST Reactor Technology | #VALUE! | #VALUE!
|  |  | x | x | 1 | 1.1.2 | High Temperature Gas-cooled Reactor (HTGR) Technology | Development of non-Light Water Reactor (LWR) Training for Advanced Reactors (Adv. Rxs) (NEIMA Section 103(a)(5)) | High Temperature Gas-cooled Reactor (HTGR) Technology | #VALUE! | #VALUE!
|  |  | x | x | 1 | 1.1.3 | Molten Salt Reactor (MSR) Technology | Development of non-Light Water Reactor (LWR) Training for Advanced Reactors (Adv. Rxs) (NEIMA Section 103(a)(5)) | Molten Salt Reactor (MSR) Technology | #VALUE! | #VALUE!
|  |  |  | x | 1 | 1.2 | Competency Modeling to ensure adequate workforce skillset | Competency Modeling to ensure adequate workforce skillset | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 1 | 1.3 | Knowledge Management | Knowledge Management | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 2 | 2.1 | Identification and Assessment of Available Codes | Identification and Assessment of Available Codes | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 2 | 2.2 | Development of Non-LWR Computer Models and Analytical Tools | Development of Non-LWR Computer Models and Analytical Tools | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 2 | 2.2.1 | Code Assessment Report Volume 1 (Systems Analysis) | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 1 (Systems Analysis) | #VALUE! | #VALUE!
|  |  |  | x | 2 | 2.2.1.1 | Reference plant model for Heat Pipe-Cooled Micro Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 1 (Systems Analysis) | Reference plant model for Heat Pipe-Cooled Micro Reactor | #VALUE!
|  |  |  | x | 2 | 2.2.1.2 | Reference plant model for Sodium-Cooled Fast Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 1 (Systems Analysis) | Reference plant model for Sodium-Cooled Fast Reactor | #VALUE!
|  |  |  | x | 2 | 2.2.1.3 | Reference plant model for Molten-Salt Cooled Pebble Bed Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 1 (Systems Analysis) | Reference plant model for Molten-Salt Cooled Pebble Bed Reactor | #VALUE!
[5 empty] | 2 | 2.2.1.4 | Reference plant model for Monolith-type Micro-Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 1 (Systems Analysis) | Reference plant model for Monolith-type Micro-Reactor | #VALUE!
[5 empty] | 2 | 2.2.1.5 | Reference plant model for Gas-Cooled Pebble Bed Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 1 (Systems Analysis) | Reference plant model for Gas-Cooled Pebble Bed Reactor | #VALUE!
[5 empty] | 2 | 2.2.2 | Code Assessment Report Volume 2 (Fuel Perf. Anaylsis) | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 2 (Fuel Perf. Anaylsis) | #VALUE! | #VALUE!
|  |  |  | x | 2 | 2.2.2.1 | FAST code assessment for metallic fuel | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 2 (Fuel Perf. Anaylsis) | FAST code assessment for metallic fuel | #VALUE!
|  |  |  | x | 2 | 2.2.2.2 | FAST code assessment for TRISO fuel | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 2 (Fuel Perf. Anaylsis) | FAST code assessment for TRISO fuel | #VALUE!
[5 empty] | 2 | 2.2.3 | Code Assessment Report Volume 3 (Source Term Analysis) | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | #VALUE! | #VALUE!
[5 empty] | 2 | 2.2.3.1 | Non-LWR MELCOR (Source Term) Demonstration Project | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | Non-LWR MELCOR (Source Term) Demonstration Project | #VALUE!
|  |  |  | x | 2 | 2.2.3.1.1 | Reference SCALE/MELCOR plant model for Heat Pipe-Cooled Micro Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | Non-LWR MELCOR (Source Term) Demonstration Project | Reference SCALE/MELCOR plant model for Heat Pipe-Cooled Micro Reactor
|  |  |  | x | 2 | 2.2.3.1.2 | Reference SCALE/MELCOR plant model for High-Temperature Gas-Cooled Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | Non-LWR MELCOR (Source Term) Demonstration Project | Reference SCALE/MELCOR plant model for High-Temperature Gas-Cooled Reactor
|  |  |  | x | 2 | 2.2.3.1.3 | Reference SCALE/MELCOR plant model for Molten Salt Cooled Pebble Bed Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | Non-LWR MELCOR (Source Term) Demonstration Project | Reference SCALE/MELCOR plant model for Molten Salt Cooled Pebble Bed Reactor
[5 empty] | 2 | 2.2.3.1.4 | Reference SCALE/MELCOR plant model for Molten Salt Fueled Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | Non-LWR MELCOR (Source Term) Demonstration Project | Reference SCALE/MELCOR plant model for Molten Salt Fueled Reactor
[5 empty] | 2 | 2.2.3.1.5 | Reference SCALE/MELCOR plant model for Sodium-Cooled Fast Reactor | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | Non-LWR MELCOR (Source Term) Demonstration Project | Reference SCALE/MELCOR plant model for Sodium-Cooled Fast Reactor
|  |  |  | x | 2 | 2.2.3.2 | MACCS radionuclide screening analysis | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | MACCS radionuclide screening analysis | #VALUE!
|  |  |  | x | 2 | 2.2.3.3 | MACCS near-field atmospheric transport and dispersion model | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | MACCS near-field atmospheric transport and dispersion model | #VALUE!
[5 empty] | 2 | 2.2.3.4 | MACCS radionuclide properties on atmospheric transport and dosimetry | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 3 (Source Term Analysis) | MACCS radionuclide properties on atmospheric transport and dosimetry | #VALUE!
[5 empty] | 2 | 2.2.4 | Code Assessment Report Volume 4 (Licensing and Siting Dose Assessments) | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 4 (Licensing and Siting Dose Assessments) | #VALUE! | #VALUE!
[5 empty] | 2 | 2.2.4.1 | Phase 1 - Atmospheric Code Consolidation | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 4 (Licensing and Siting Dose Assessments) | Phase 1 - Atmospheric Code Consolidation | #VALUE!
|  |  |  | x | 2 | 2.2.5 | Code Assessment Report Volume 5 (Fuel Cycle Analysis) | Development of Non-LWR Computer Models and Analytical Tools | Code Assessment Report Volume 5 (Fuel Cycle Analysis) | #VALUE! | #VALUE!
|  |  |  | x | 2 | 2.3 | Research plan and accomplishments in Materials, Chemistry, and Component Integrity for Adv. Rxs. | Research plan and accomplishments in Materials, Chemistry, and Component Integrity for Adv. Rxs. | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 2 | 2.4 | Research on risk-informed and performance-based (RIPB) seismic design approaches and adopting seismic isolation technologies | Research on risk-informed and performance-based (RIPB) seismic design approaches and adopting seismic isolation technologies | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | 3 | 3.01 | Develop Regulatory Roadmap for Adv. Rxs (NEIMA Section 103(a)(1)) | Develop Regulatory Roadmap for Adv. Rxs (NEIMA Section 103(a)(1)) | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.02 | Develop prototype guidance for Adv. Rxs | Develop prototype guidance for Adv. Rxs | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.03 | Develop non-LWR Design Crtieria for Adv. Rxs | Develop non-LWR Design Crtieria for Adv. Rxs | #VALUE! | #VALUE! | #VALUE!
| x |  |  | x | 3 | 3.04 | EPRI Topical Report on Tri-structural Isotropic (TRISO) Fuel | EPRI Topical Report on Tri-structural Isotropic (TRISO) Fuel | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.05 | Quality Assurance Program Plan for Sodium-cooled FAST Reactor Metallic Fuel Data Qualification | Quality Assurance Program Plan for Sodium-cooled FAST Reactor Metallic Fuel Data Qualification | #VALUE! | #VALUE! | #VALUE!
| x |  | x |  | 3 | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246) | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246) | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 3 | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 3 | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 3 | 3.09 | Develop non-LWR Construction Permit Guidance | Develop non-LWR Construction Permit Guidance | #VALUE! | #VALUE! | #VALUE!
| x |  |  | x | 3 | 3.10 | Develop non-LWR Design Review Guide (DRG) for Instrumentation and Controls reviews | Develop non-LWR Design Review Guide (DRG) for Instrumentation and Controls reviews | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 3 | 3.11 | Develop Advanced Reactor Inspection and Oversight Framework Document | Develop Advanced Reactor Inspection and Oversight Framework Document | #VALUE! | #VALUE! | #VALUE!
| x |  |  | x | 3 | 3.12 | Develop Environmental ISG for Micro Reactors | Develop Environmental ISG for Micro Reactors | #VALUE! | #VALUE! | #VALUE!
| x |  |  | x | 3 | 3.13 | Develop Regulatory Guide for Licensing Modernization Project | Develop Regulatory Guide for Licensing Modernization Project | #VALUE! | #VALUE! | #VALUE!
| x |  | x | x | 3 | 3.14 | Develop non-LWR Source Term Information (NEIMA Section 103(c)(4)(II) | Develop non-LWR Source Term Information (NEIMA Section 103(c)(4)(II) | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 3 | 3.15 | Develop Molten Salt Reactor fuel qualification guidance | Develop Molten Salt Reactor fuel qualification guidance | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.15.1 | Interim MSR fuel qualification guidance | Develop Molten Salt Reactor fuel qualification guidance | Interim MSR fuel qualification guidance | #VALUE! | #VALUE!
[5 empty] | 3 | 3.15.2 | Final MSR fuel qualification guidance | Develop Molten Salt Reactor fuel qualification guidance | Final MSR fuel qualification guidance | #VALUE! | #VALUE!
| x |  | x | x | 3 | 3.16 | Develop guidance for Non-power Liquid Fueled Molten Salt Reactors (NEIMA Section 103(a)(3)) | Develop guidance for Non-power Liquid Fueled Molten Salt Reactors (NEIMA Section 103(a)(3)) | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 3 | 3.17 | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.01 | Develop Report on possible Material Control and Accounting Approaches for a Pebble Bed Reactor. | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Develop Report on possible Material Control and Accounting Approaches for a Pebble Bed Reactor. | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.02 | Develop Metal Fuel Fabrication Safety and Hazards Final Report | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Develop Metal Fuel Fabrication Safety and Hazards Final Report | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.03 | Develop Review of Hazards for Molten Salt Reactor Fuel Processing Operations | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Develop Review of Hazards for Molten Salt Reactor Fuel Processing Operations | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.04 | Review of Operating Experience for Transportation of Fresh (Unirradiated) Advanced Reactor Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Review of Operating Experience for Transportation of Fresh (Unirradiated) Advanced Reactor Fuel Types | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.05 | Potential Challenges with Transportation of Fresh (Unirradiated) Advanced Reactor Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Potential Challenges with Transportation of Fresh (Unirradiated) Advanced Reactor Fuel Types | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.06 | Storage Experience with Spent (Irradiated) Advanced Reactor Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Storage Experience with Spent (Irradiated) Advanced Reactor Fuel Types | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.07 | Potential Challenges with Storage of Spent (Irradiated) Advanced Reactor Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Potential Challenges with Storage of Spent (Irradiated) Advanced Reactor Fuel Types | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.08 | Transportation Experience and Potential Challenges with Transportation of Spent (Irradiated) Advanced Reactor Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Transportation Experience and Potential Challenges with Transportation of Spent (Irradiated) Advanced Reactor Fuel Types | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.09 | Disposal Options and Potential Challenges to Waste Packages and Waste Forms in Disposal of Spent (Irradiated) Advanced Reactor Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Disposal Options and Potential Challenges to Waste Packages and Waste Forms in Disposal of Spent (Irradiated) Advanced Reactor Fuel Types | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.17.10 | Information Gaps and Potential Information Needs Associated with Transportation of Fresh (Unirradiated) Adv. Rx Fuel Types | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Information Gaps and Potential Information Needs Associated with Transportation of Fresh (Unirradiated) Adv. Rx Fuel Types | #VALUE! | #VALUE!
[5 empty] | 3 | 3.17.11 | Develop MC&A guidance for Cat II facilities (NUREG-2159) | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure. | Develop MC&A guidance for Cat II facilities (NUREG-2159) | #VALUE! | #VALUE!
|  |  |  | x | 3 | 3.18 | Develop contractor report on technology-inclusive human factors engineering reviews | Develop contractor report on technology-inclusive human factors engineering reviews | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 4 | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 4 | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard | #VALUE! | #VALUE! | #VALUE!
| x |  |  |  | 4 | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898) | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard | Alloy 617 Code Cases (N-872 and N-898) | #VALUE! | #VALUE!
[5 empty] | 4 | 4.3 | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM) | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM) | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 5 | 5.1 | Develop SECY paper related to Consequence Based Security (SECY-18-0076) | Develop SECY paper related to Consequence Based Security (SECY-18-0076) | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | 5 | 5.2 | Develop SECY paper related to EP for Small Modular Reactors and Other New Technologies (SECY-18-0103) | Develop SECY paper related to EP for Small Modular Reactors and Other New Technologies (SECY-18-0103) | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | 5 | 5.3 | Develop SECY paper related to Functional Containment (SECY-18-0096) | Develop SECY paper related to Functional Containment (SECY-18-0096) | #VALUE! | #VALUE! | #VALUE!
x |  |  |  | x | 5 | 5.4 | SECY-20-0093 Policy and Licensing Considerations related to Micro Reactors | SECY-20-0093 Policy and Licensing Considerations related to Micro Reactors | #VALUE! | #VALUE! | #VALUE!
x |  |  |  |  | 5 | 5.5 | Report regarding review of the insurance and liability for advanced reactors (Price-Anderson Act) | Report regarding review of the insurance and liability for advanced reactors (Price-Anderson Act) | #VALUE! | #VALUE! | #VALUE!
[5 empty] | 5 | 5.6 | Annual Fees for Non-Light Water Reactors and Microreactors | Annual Fees for Non-Light Water Reactors and Microreactors | #VALUE! | #VALUE! | #VALUE!
x |  |  |  |  | 5 | 5.7 | Develop SECY Paper regarding Population-Related Siting Considerations for Advanced Reactors | Develop SECY Paper regarding Population-Related Siting Considerations for Advanced Reactors | #VALUE! | #VALUE! | #VALUE!
x |  |  |  |  | 6 | 6.1 | Develop annual SECY paper regarding status of non-LWR activities | Develop annual SECY paper regarding status of non-LWR activities | #VALUE! | #VALUE! | #VALUE!
|  |  |  | x | 6 | 6.2 | NRC DOE Workshops | NRC DOE Workshops | #VALUE! | #VALUE! | #VALUE!
|  | x | x |  | Rulemaking | 7.1 | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4)) | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4)) | #VALUE! | #VALUE! | #VALUE!
[5 empty] | Rulemaking | 7.1.1 | Public Meetings | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4)) | Public Meetings | #VALUE! | #VALUE!
[5 empty] | Rulemaking | 7.1.2 | ACRS Interactions | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4)) | ACRS Interactions | #VALUE! | #VALUE!
|  | x |  |  | Rulemaking | 7.2 | Physical Security for Advanced Reactors | Physical Security for Advanced Reactors | #VALUE! | #VALUE! | #VALUE!
|  | x | x |  | Rulemaking | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2)) | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2)) | #VALUE! | #VALUE! | #VALUE!
[5 empty] | Rulemaking | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | NEIMA Reporting | 8.1 | Provide report to Congress regarding licensing processes for Advanced Reactors (NEIMA Section 103(b)) | Provide report to Congress regarding licensing processes for Advanced Reactors (NEIMA Section 103(b)) | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | NEIMA Reporting | 8.2 | Provide report to Congress regarding the use of risk-informed and performance based techniques for Adv. Rx. Licensing (NEIMA Section 103(c)) | Provide report to Congress regarding the use of risk-informed and performance based techniques for Adv. Rx. Licensing (NEIMA Section 103(c)) | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | NEIMA Reporting | 8.3 | Provide report to Congress on preparing the licensing process for RTRs within existing Regulatory Framework (NEIMA Section 103(d)) | Provide report to Congress on preparing the licensing process for RTRs within existing Regulatory Framework (NEIMA Section 103(d)) | #VALUE! | #VALUE! | #VALUE!
|  |  | x | x | NEIMA Reporting | 8.4 | Provide report to Congress on completing the rulemaking to establish a "technology-inclusive regulatory framework" (NEIMA Section 103(e)) | Provide report to Congress on completing the rulemaking to establish a "technology-inclusive regulatory framework" (NEIMA Section 103(e)) | #VALUE! | #VALUE! | #VALUE!

## Start End Date
Start Date | End Date | Project | Activity Level | Regulatory Activity
|  |  | 1.1 | Development of non-Light Water Reactor (LWR) Training for Advanced Reactors (Adv. Rxs) (NEIMA Section 103(a)(5))
|  |  | 1.1.1 | FAST Reactor Technology
|  |  | 1.1.2 | High Temperature Gas-cooled Reactor (HTGR) Technology
|  |  | 1.1.3 | Molten Salt Reactor (MSR) Technology
|  |  | 1.2 | Competency Modeling to ensure adequate workforce skillset
2021-01-01 | 2022-12-31 | Final Issuance of Deliverable | 1.3 | Knowledge Management
|  |  | 2.1 | Identification and Assessment of Available Codes
|  |  | 2.2 | Development of Non-LWR Computer Models and Analytical Tools
|  |  | 2.2.1 | Code Assessment Report Volume 1 (Systems Analysis)
|  |  | 2.2.1.1 | Reference plant model for Heat Pipe-Cooled Micro Reactor
|  |  | 2.2.1.2 | Reference plant model for Sodium-Cooled Fast Reactor
|  |  | 2.2.1.3 | Reference plant model for Molten-Salt Cooled Pebble Bed Reactor
2022-03-01 | 2022-03-31 | Final Issuance of Deliverable | 2.2.1.4 | Reference plant model for Monolith-type Micro-Reactor
2022-06-01 | 2022-06-30 | Final Issuance of Deliverable | 2.2.1.5 | Reference plant model for Gas-Cooled Pebble Bed Reactor
|  |  | 2.2.2 | Code Assessment Report Volume 2 (Fuel Perf. Anaylsis)
|  |  | 2.2.2.1 | FAST code assessment for metallic fuel
|  |  | 2.2.2.1 | FAST code assessment for metallic fuel
|  |  | 2.2.2.2 | FAST code assessment for TRISO fuel
|  |  | 2.2.3 | Code Assessment Report Volume 3 (Source Term Analysis)
2021-06-15 | 2021-06-15 | Public Meeting (Scheduled or Planned) | 2.2.3.1 | Non-LWR MELCOR (Source Term) Demonstration Project
2021-07-15 | 2021-07-15 | Public Meeting (Scheduled or Planned) | 2.2.3.1 | Non-LWR MELCOR (Source Term) Demonstration Project
2021-09-15 | 2021-09-15 | Public Meeting (Scheduled or Planned) | 2.2.3.1 | Non-LWR MELCOR (Source Term) Demonstration Project
2021-09-01 | 2021-09-30 | Final Issuance of Deliverable | 2.2.3.1 | Non-LWR MELCOR (Source Term) Demonstration Project
|  |  | 2.2.3.1.1 | Reference SCALE/MELCOR plant model for Heat Pipe-Cooled Micro Reactor
|  |  | 2.2.3.1.2 | Reference SCALE/MELCOR plant model for High-Temperature Gas-Cooled Reactor
|  |  | 2.2.3.1.3 | Reference SCALE/MELCOR plant model for Molten Salt Cooled Pebble Bed Reactor
2021-11-01 | 2021-11-30 | Final Issuance of Deliverable | 2.2.3.1.4 | Reference SCALE/MELCOR plant model for Molten Salt Fueled Reactor
2022-06-01 | 2022-06-30 | Final Issuance of Deliverable | 2.2.3.1.5 | Reference SCALE/MELCOR plant model for Sodium-Cooled Fast Reactor
2021-09-01 | 2021-09-30 | Final Issuance of Deliverable | 2.2.3.2 | MACCS radionuclide screening analysis
|  |  | 2.2.3.3 | MACCS near-field atmospheric transport and dispersion model
2022-06-01 | 2022-09-30 | Final Issuance of Deliverable | 2.2.3.4 | MACCS radionuclide properties on atmospheric transport and dosimetry
|  |  | 2.2.4 | Code Assessment Report Volume 4 (Licensing and Siting Dose Assessments)
|  |  | 2.2.4 | Code Assessment Report Volume 4 (Licensing and Siting Dose Assessments)
|  |  | 2.2.4 | Code Assessment Report Volume 4 (Licensing and Siting Dose Assessments)
2022-07-01 | 2022-07-31 | Final Issuance of Deliverable | 2.2.4.1 | Phase 1 - Atmospheric Code Consolidation
|  |  | 2.2.5 | Code Assessment Report Volume 5 (Fuel Cycle Analysis)
|  |  | 2.2.5 | Code Assessment Report Volume 5 (Fuel Cycle Analysis)
|  |  | 2.2.5 | Code Assessment Report Volume 5 (Fuel Cycle Analysis)
|  |  | 2.2.5 | Code Assessment Report Volume 5 (Fuel Cycle Analysis)
|  |  | 2.3 | Research plan and accomplishments in Materials, Chemistry, and Component Integrity for Adv. Rxs.
2020-04-01 | 2020-04-30 | Federal Register Publication | 2.4 | Research on risk-informed and performance-based (RIPB) seismic design approaches and adopting seismic isolation technologies
2020-09-01 | 2020-09-30 | Public Meeting (Scheduled or Planned) | 2.4 | Research on risk-informed and performance-based (RIPB) seismic design approaches and adopting seismic isolation technologies
2022-07-01 | 2022-07-31 | Draft Issuance of Deliverable | 2.4 | Research on risk-informed and performance-based (RIPB) seismic design approaches and adopting seismic isolation technologies
|  |  | 3.01 | Develop Regulatory Roadmap for Adv. Rxs (NEIMA Section 103(a)(1))
|  |  | 3.02 | Develop prototype guidance for Adv. Rxs
|  |  | 3.03 | Develop non-LWR Design Crtieria for Adv. Rxs
|  |  | 3.04 | EPRI Topical Report on Tri-structural Isotropic (TRISO) Fuel
|  |  | 3.05 | Quality Assurance Program Plan for Sodium-cooled FAST Reactor Metallic Fuel Data Qualification
2020-09-01 | 2020-09-30 | Draft Issuance of Deliverable | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2020-10-14 | 2020-10-14 | Public Meeting (Scheduled or Planned) | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-02-14 | 2021-02-14 | ACRS SC/FC (Scheduled or Planned) | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-03-01 | 2021-05-31 | Concurrence (Division/Interoffice) | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-06-01 | 2021-06-30 | Federal Register Publication | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-07-01 | 2021-08-31 | Public Comment Period | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-09-15 | 2021-09-15 | Public Meeting (Scheduled or Planned) | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-10-01 | 2022-01-31 | Concurrence (Division/Interoffice) | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2021-11-14 | 2021-11-14 | ACRS SC/FC (Scheduled or Planned) | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2022-02-01 | 2022-02-28 | Final Issuance of Deliverable | 3.06 | Develop Fuel Qualification Guidance for Adv. Rxs (NUREG-2246)
2020-02-14 | 2020-02-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-04-14 | 2020-04-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-06-14 | 2020-06-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-07-14 | 2020-07-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-08-14 | 2020-08-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-10-14 | 2020-10-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-12-14 | 2020-12-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-02-14 | 2021-02-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-03-14 | 2021-03-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-04-14 | 2021-04-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-04-01 | 2021-04-30 | Draft Issuance of Deliverable | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-06-14 | 2021-06-14 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-07-14 | 2021-07-14 | ACRS SC/FC (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-10-01 | 2021-10-31 | Draft Issuance of Deliverable | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-11-10 | 2021-11-10 | Public Meeting (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-11-01 | 2021-12-31 | Concurrence (Division/Interoffice) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2021-12-14 | 2021-12-14 | ACRS SC/FC (Scheduled or Planned) | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2022-05-01 | 2022-05-31 | Final Issuance of Deliverable | 3.07 | Develop Advanced Reactor Content of Application Project (ARCAP) Regulatory Guidance
2020-02-14 | 2020-02-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2020-04-14 | 2020-04-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2020-06-14 | 2020-06-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2020-07-14 | 2020-07-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2020-08-14 | 2020-08-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2020-10-14 | 2020-10-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2020-12-14 | 2020-12-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-02-14 | 2021-02-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-03-14 | 2021-03-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-04-14 | 2021-04-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-04-01 | 2021-04-30 | Draft Issuance of Deliverable | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-05-14 | 2021-05-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-06-14 | 2021-06-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-07-14 | 2021-07-14 | ACRS SC/FC (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-08-14 | 2021-08-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-09-14 | 2021-09-14 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-10-01 | 2021-10-31 | Draft Issuance of Deliverable | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-11-09 | 2021-11-09 | Public Meeting (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-11-01 | 2021-12-31 | Concurrence (Division/Interoffice) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-12-14 | 2021-12-14 | ACRS SC/FC (Scheduled or Planned) | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2022-05-01 | 2022-05-30 | Final Issuance of Deliverable | 3.08 | Develop Advanced Reactor Technology Inclusive Content of Application Project (TICAP) Regulatory Guidance
2021-04-01 | 2021-04-30 | Draft Issuance of Deliverable | 3.09 | Develop non-LWR Construction Permit Guidance
2021-07-14 | 2021-07-14 | ACRS SC/FC (Scheduled or Planned) | 3.09 | Develop non-LWR Construction Permit Guidance
2021-10-01 | 2021-10-31 | Draft Issuance of Deliverable | 3.09 | Develop non-LWR Construction Permit Guidance
2021-11-01 | 2021-12-31 | Concurrence (Division/Interoffice) | 3.09 | Develop non-LWR Construction Permit Guidance
2021-12-14 | 2021-12-14 | ACRS SC/FC (Scheduled or Planned) | 3.09 | Develop non-LWR Construction Permit Guidance
2022-05-01 | 2022-05-30 | Final Issuance of Deliverable | 3.09 | Develop non-LWR Construction Permit Guidance
2021-01-01 | 2021-02-28 | Draft Issuance of Deliverable | 3.10 | Develop non-LWR Design Review Guide (DRG) for Instrumentation and Controls reviews
2021-03-01 | 2021-03-31 | Final Issuance of Deliverable | 3.10 | Develop non-LWR Design Review Guide (DRG) for Instrumentation and Controls reviews
2021-05-14 | 2021-05-14 | Public Meeting (Scheduled or Planned) | 3.11 | Develop Advanced Reactor Inspection and Oversight Framework Document
2021-12-01 | 2021-12-31 | Draft Issuance of Deliverable | 3.11 | Develop Advanced Reactor Inspection and Oversight Framework Document
|  |  | 3.12 | Develop Environmental ISG for Micro Reactors
|  |  | 3.13 | Develop Regulatory Guide for Licensing Modernization Project
|  |  | 3.14 | Develop non-LWR Source Term Information (NEIMA Section 103(c)(4)(II)
|  |  | 3.15 | Develop Molten Salt Reactor fuel qualification guidance
|  |  | 3.15.1 | Interim MSR fuel qualification guidance
2021-09-01 | 2021-09-30 | Draft Issuance of Deliverable | 3.15.2 | Final MSR fuel qualification guidance
2021-10-14 | 2021-10-14 | ACRS SC/FC (Scheduled or Planned) | 3.15.2 | Final MSR fuel qualification guidance
|  |  | 3.16 | Develop guidance for Non-power Liquid Fueled Molten Salt Reactors (NEIMA Section 103(a)(3))
|  |  | 3.17 | Review of non-LWR Fuel Cycle Assessment of Regulatory Infrastructure.
|  |  | 3.17.01 | Develop Report on possible Material Control and Accounting Approaches for a Pebble Bed Reactor.
|  |  | 3.17.02 | Develop Metal Fuel Fabrication Safety and Hazards Final Report
|  |  | 3.17.03 | Develop Review of Hazards for Molten Salt Reactor Fuel Processing Operations
|  |  | 3.17.04 | Review of Operating Experience for Transportation of Fresh (Unirradiated) Advanced Reactor Fuel Types
|  |  | 3.17.05 | Potential Challenges with Transportation of Fresh (Unirradiated) Advanced Reactor Fuel Types
|  |  | 3.17.06 | Storage Experience with Spent (Irradiated) Advanced Reactor Fuel Types
|  |  | 3.17.07 | Potential Challenges with Storage of Spent (Irradiated) Advanced Reactor Fuel Types
|  |  | 3.17.08 | Transportation Experience and Potential Challenges with Transportation of Spent (Irradiated) Advanced Reactor Fuel Types
|  |  | 3.17.09 | Disposal Options and Potential Challenges to Waste Packages and Waste Forms in Disposal of Spent (Irradiated) Advanced Reactor Fuel Types
|  |  | 3.17.10 | Information Gaps and Potential Information Needs Associated with Transportation of Fresh (Unirradiated) Adv. Rx Fuel Types
2021-09-01 | 2021-09-30 | Draft Issuance of Deliverable | 3.17.11 | Develop MC&A guidance for Cat II facilities (NUREG-2159)
2021-10-01 | 2021-11-30 | Public Comment Period | 3.17.11 | Develop MC&A guidance for Cat II facilities (NUREG-2159)
2021-12-01 | 2021-12-31 | Final Issuance of Deliverable | 3.17.11 | Develop MC&A guidance for Cat II facilities (NUREG-2159)
2021-02-01 | 2021-02-28 | Draft Issuance of Deliverable | 3.18 | Develop contractor report on technology-inclusive human factors engineering reviews
2021-04-01 | 2021-04-30 | Final Issuance of Deliverable | 3.18 | Develop contractor report on technology-inclusive human factors engineering reviews
2021-06-01 | 2021-06-30 | Final Issuance of Deliverable | 3.18 | Develop contractor report on technology-inclusive human factors engineering reviews
2020-06-14 | 2020-06-14 | Public Meeting (Scheduled or Planned) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2020-11-14 | 2020-11-14 | ACRS SC/FC (Scheduled or Planned) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2021-02-14 | 2021-02-14 | Public Meeting (Scheduled or Planned) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2021-08-14 | 2021-08-14 | Public Meeting (Scheduled or Planned) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2021-09-14 | 2021-09-14 | ACRS SC/FC (Scheduled or Planned) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2021-11-03 | 2021-11-03 | Public Meeting (Scheduled or Planned) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2021-09-01 | 2021-11-30 | Concurrence (Division/Interoffice) | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2021-12-01 | 2021-12-31 | Draft Issuance of Deliverable | 4.1 | Develop Regulatory Guide for endorsement of the non-LWR Probabilistic Risk Assessment Standard
2020-10-14 | 2020-10-14 | Public Meeting (Scheduled or Planned) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2020-11-14 | 2020-11-14 | Public Meeting (Scheduled or Planned) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-01-14 | 2021-01-14 | Public Meeting (Scheduled or Planned) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-04-01 | 2021-07-31 | Concurrence (Division/Interoffice) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-07-14 | 2021-07-14 | ACRS SC/FC (Scheduled or Planned) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-08-01 | 2021-08-31 | Federal Register Publication | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-09-01 | 2021-10-31 | Public Comment Period | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-11-01 | 2021-12-31 | Concurrence (Division/Interoffice) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-12-01 | 2022-04-30 | Final Issuance of Deliverable | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-07-01 | 2021-08-31 | Concurrence (Division/Interoffice) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2022-04-14 | 2022-04-14 | ACRS SC/FC (Scheduled or Planned) | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2022-05-01 | 2022-05-31 | Final Issuance of Deliverable | 4.2 | Develop Regulatory Guide for endorsement of the ASME Section III, Division 5 Standard
2021-12-01 | 2021-12-31 | Draft Issuance of Deliverable | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898)
2022-01-01 | 2022-01-31 | Federal Register Publication | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898)
2022-02-01 | 2022-02-28 | Public Comment Period | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898)
2022-03-01 | 2022-04-30 | Concurrence (Division/Interoffice) | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898)
2022-04-14 | 2022-04-14 | ACRS SC/FC (Scheduled or Planned) | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898)
2022-05-01 | 2022-05-31 | Final Issuance of Deliverable | 4.2.1 | Alloy 617 Code Cases (N-872 and N-898)
2021-07-01 | 2021-08-31 | Concurrence (Division/Interoffice) | 4.3 | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM)
2021-09-01 | 2021-09-30 | Federal Register Publication | 4.3 | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM)
2021-10-01 | 2021-11-30 | Public Comment Period | 4.3 | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM)
2022-05-01 | 2022-05-31 | Concurrence (Division/Interoffice) | 4.3 | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM)
2022-06-01 | 2022-06-30 | Final Issuance of Deliverable | 4.3 | Develop Draft Guide endorsing ASME Section XI Division 2 Reliability and Integrity Management (RIM)
|  |  | 5.1 | Develop SECY paper related to Consequence Based Security (SECY-18-0076)
|  |  | 5.2 | Develop SECY paper related to EP for Small Modular Reactors and Other New Technologies (SECY-18-0103)
|  |  | 5.3 | Develop SECY paper related to Functional Containment (SECY-18-0096)
|  |  | 5.4 | SECY-20-0093 Policy and Licensing Considerations related to Micro Reactors
2021-06-01 | 2021-07-31 | Concurrence (Division/Interoffice) | 5.5 | Report regarding review of the insurance and liability for advanced reactors (Price-Anderson Act)
2021-08-01 | 2021-11-30 | Commission Review Period** | 5.5 | Report regarding review of the insurance and liability for advanced reactors (Price-Anderson Act)
2021-12-01 | 2021-12-31 | Final Issuance of Deliverable | 5.5 | Report regarding review of the insurance and liability for advanced reactors (Price-Anderson Act)
2020-05-14 | 2020-05-14 | Public Meeting (Scheduled or Planned) | 5.6 | Annual Fees for Non-Light Water Reactors and Microreactors
2020-06-14 | 2020-06-14 | Public Meeting (Scheduled or Planned) | 5.6 | Annual Fees for Non-Light Water Reactors and Microreactors
2020-08-14 | 2020-08-14 | Public Meeting (Scheduled or Planned) | 5.6 | Annual Fees for Non-Light Water Reactors and Microreactors
2021-04-15 | 2021-04-15 | Public Meeting (Scheduled or Planned) | 5.6 | Annual Fees for Non-Light Water Reactors and Microreactors
2021-07-15 | 2021-07-15 | Public Meeting (Scheduled or Planned) | 5.6 | Annual Fees for Non-Light Water Reactors and Microreactors
2020-01-01 | 2020-04-30 | Concurrence (Division/Interoffice) | 5.7 | Develop SECY Paper regarding Population-Related Siting Considerations for Advanced Reactors
2020-05-01 | 2020-05-31 | Final Issuance of Deliverable | 5.7 | Develop SECY Paper regarding Population-Related Siting Considerations for Advanced Reactors
2020-06-01 | 2021-10-31 | Commission Review Period** | 5.7 | Develop SECY Paper regarding Population-Related Siting Considerations for Advanced Reactors
2020-10-01 | 2020-12-31 | Concurrence (Division/Interoffice) | 6.1 | Develop annual SECY paper regarding status of non-LWR activities
2021-01-01 | 2021-01-31 | Final Issuance of Deliverable | 6.1 | Develop annual SECY paper regarding status of non-LWR activities
2022-01-01 | 2022-01-31 | Final Issuance of Deliverable | 6.1 | Develop annual SECY paper regarding status of non-LWR activities
|  |  | 6.2 | NRC DOE Workshops
2022-02-01 | 2022-05-31 | Concurrence (Division/Interoffice) | 7.1 | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4))
2022-05-01 | 2022-05-31 | EDO Concurrence Period | 7.1 | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4))
2022-06-01 | 2022-08-31 | Commission Review Period** | 7.1 | Part 53 Plan - Risk-Informed, Technology Inclusive Regulatory Framework for Advanced Reactors (NEIMA Section 103(a)(4))
2020-11-14 | 2020-11-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-01-14 | 2021-01-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-02-14 | 2021-02-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-04-14 | 2021-04-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-05-14 | 2021-05-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-06-14 | 2021-06-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-09-14 | 2021-09-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2021-10-14 | 2021-10-14 | Public Meeting (Scheduled or Planned) | 7.1.1 | Public Meetings
2020-07-14 | 2020-07-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2020-09-14 | 2020-09-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-01-14 | 2021-01-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-02-14 | 2021-02-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-03-14 | 2021-03-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-04-14 | 2021-04-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-05-14 | 2021-05-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-07-14 | 2021-07-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-09-14 | 2021-09-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-10-14 | 2021-10-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-11-18 | 2021-11-18 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2021-12-16 | 2021-12-16 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2022-01-14 | 2022-01-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2022-02-14 | 2022-02-14 | ACRS SC/FC (Scheduled or Planned) | 7.1.2 | ACRS Interactions
2020-04-14 | 2020-04-14 | Public Meeting (Scheduled or Planned) | 7.2 | Physical Security for Advanced Reactors
2021-06-01 | 2021-08-31 | Concurrence (Division/Interoffice) | 7.2 | Physical Security for Advanced Reactors
2021-09-01 | 2021-09-30 | Draft Issuance of Deliverable | 7.2 | Physical Security for Advanced Reactors
2021-09-01 | 2021-09-30 | EDO Concurrence Period | 7.2 | Physical Security for Advanced Reactors
2021-10-01 | 2021-12-31 | Commission Review Period** | 7.2 | Physical Security for Advanced Reactors
2020-01-01 | 2020-04-30 | Commission Review Period** | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2020-05-01 | 2020-05-31 | Federal Register Publication | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2020-06-14 | 2020-06-14 | Public Meeting (Scheduled or Planned) | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2020-06-01 | 2020-09-30 | Public Comment Period | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2021-08-01 | 2021-12-31 | Concurrence (Division/Interoffice) | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2021-09-14 | 2021-09-14 | ACRS SC/FC (Scheduled or Planned) | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2021-11-14 | 2021-11-14 | ACRS SC/FC (Scheduled or Planned) | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2021-12-01 | 2021-12-31 | EDO Concurrence Period | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2022-01-01 | 2022-01-31 | Commission Review Period** | 7.3 | Emergency Preparedness Requirements for Small Modular Reactors and Other New Technologies.(NEIMA Section 103(a)(2))
2020-04-01 | 2020-04-30 | Federal Register Publication | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS
2020-05-01 | 2020-06-30 | Public Comment Period | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS
2020-05-14 | 2020-05-14 | Public Meeting (Scheduled or Planned) | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS
2021-04-14 | 2021-04-14 | Public Meeting (Scheduled or Planned) | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS
2021-07-14 | 2021-07-14 | Public Meeting (Scheduled or Planned) | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS
2022-05-01 | 2022-05-31 | Draft Issuance of Deliverable | 7.4 | Develop draft Generic Environmental Impact Statement for Advanced Reactors. Final GEIS
|  |  | 8.1 | Provide report to Congress regarding licensing processes for Advanced Reactors (NEIMA Section 103(b))
|  |  | 8.2 | Provide report to Congress regarding the use of risk-informed and performance based techniques for Adv. Rx. Licensing (NEIMA Section 103(c))
|  |  | 8.3 | Provide report to Congress on preparing the licensing process for RTRs within existing Regulatory Framework (NEIMA Section 103(d))
|  |  | 8.4 | Provide report to Congress on completing the rulemaking to establish a "technology-inclusive regulatory framework" (NEIMA Section 103(e))
|  |  | 8.4 | Provide report to Congress on completing the rulemaking to establish a "technology-inclusive regulatory framework" (NEIMA Section 103(e))
|  |  | 8.4 | Provide report to Congress on completing the rulemaking to establish a "technology-inclusive regulatory framework" (NEIMA Section 103(e))