NRC INSPECTION MANUAL			NMSS

MANUAL CHAPTER 2696

LOUISIANA ENERGY SERVICES GAS CENTRIFUGE FACILITY CONSTRUCTION AND PRE-OPERATIONAL READINESS REVIEW INSPECTION PROGRAMS

2696-01	PURPOSE

Under the provisions of 10 CFR 40.41(g) and 10 CFR 70.32(k) and their license, prior to the Louisiana Energy Services (LES) National Enrichment Facility (NEF) Gas Centrifuge being allowed to operate under their license, the Commission must verify that the facility was constructed in accordance with the requirements of the license.

The purpose of this Inspection Manual Chapter (IMC) is to define the Construction Inspection Program (CIP) for the LES NEF.  Specifically, the CIP will (1) provide reasonable assurance that the design, construction, and implementation of items relied on for safety (IROFS) will protect against natural phenomena and the consequences of potential accidents, (2) verify the Quality Assurance (QA) Program was adequately implemented during construction; and (3) verify that the construction of the IROFS was completed in accordance with the documents comprising the license application (Safety Analysis Report (SAR), etc.); the Integrated Safety Analysis (ISA), the Integrated Safety Analysis Summary (ISAS), and the Safety Evaluation Report (SER).

The LES CIP applies to all construction activities, including, design, procurement, fabrication, construction, and pre-operational testing activities.  Implementation of this IMC will begin at an applicable time as determined by the NRC and will continue through facility construction activities as noted above.

2696-02	OBJECTIVES

The primary objective of this manual chapter is to establish a CIP for inspecting IROFS and inspecting associated activities that are conducted by the licensee and their consultants, contractors, and suppliers, to support the decision to allow operation of the NEF.  The following objectives are included in the CIP:

02.01	Provide reasonable assurance that regulatory requirements and licensee commitments for quality assurance and management measures are adequately included in the design, procurement, and construction of the NEF.

02.02	Provide reasonable assurance that the NEF and associated IROFS were constructed in accordance with the quality assurance program, the license application, the ISA, the ISAS, and the SER.

02.03	Verify the effective implementation of a safety program that includes the following elements:  process safety information, the ISA, and management measures.

02.04	Verify the effective implementation of the quality assurance program as specified in the LES Quality Assurance Program Description (QAPD).  Verify that this includes timely implementation of organizational staffing, procedures, instructions, QA activities, and administrative controls necessary to achieve quality objectives important to safety

02.05	Identify conditions that may adversely affect public and worker safety so that appropriate corrective actions can be taken.

02.06	Conduct risk-informed and performance-based inspections across key functional areas (see Appendix B for a listing of these areas)  to support the decision to allow operations at the NEF.

2696-03	DEFINITIONS

03.01	IROFS Boundary Packages: The IROFS boundary packages identify the specific functions to be performed by an IROFS, and identify any items that may affect the function of the IROFS.  The boundary packages include information on planned and preventive maintenance, functional testing and inspection, calibration, and support systems (including instrumentation, cooling, etc.).   They also include information on applicable management measures and records requirements for the IROFS.

03.02	In-Office (or Field) Review:  Assessments, audits, or reviews conducted to assess licensing related activities.

03.03	Inspection:  Measures consisting of examinations, observations, or measurements

to determine the conformance of materials, parts, structures, systems, components (SSCs), services, or processes to predetermined quality requirements.  Activities include performing audits, inspections, surveillances, and observations.

03.04	Inspection Types:  Inspections are classified as compliance-based or performance-based and are defined below.

- Compliance-based inspections emphasize inspection of compliance with prescriptive NRC requirements or regulatory commitments that specify IROFS, features, actions, or programmatic elements.

- Performance-based inspections emphasize inspection of actual activity performance and results.  Performance-based inspections require measurable or calculable parameters and objective performance assessment criteria.  Note that a performance-based approach does not change the need for compliance with NRC requirements.  In addition, a performance-based approach is typically more applicable to an operating facility and may not be appropriate to perform certain construction or pre-operational inspections.

03.05	Items Relied on for Safety (IROFS):  SSCs, equipment, and activities of personnel that are relied on to prevent potential accidents at a facility that could exceed the performance requirements in 10 CFR 70.61 or to mitigate their potential consequences.  This does not limit the licensee from identifying additional SSCs, equipment, or activities of personnel (i.e., beyond those in the minimum set necessary for compliance with the performance requirements) as items relied on for safety.

03.06	The License Application: The license application comprises a set of documents submitted by the licensee as listed in the license under Section 10.  These documents include the SAR, the Environmental Report, the QAPD, and the Emergency Plan.

03.07	Management Measures:  The functions performed by the licensee, generally on a continuing basis, that are applied to items relied on for safety, to ensure the items are available and reliable to perform their functions when needed.  Management measures include configuration management, maintenance, training and qualifications, procedures, audits and assessments, incident investigations, records management, and other quality assurance elements.

03.08	NEF Start-up:  Activities associated with the cold start-up or hot start-up of the NEF as defined below.

- Cold Start-up:  Pre-operational inspection, testing, or measurement activities not involving the use of licensed material in NEF process systems or components.

- Hot Start-up:  Pre-operational inspection, testing, or measurement activities involving the use of NRC licensed material in NEF systems or components.  This would include centrifuge testing using uranium hexafluoride.

03.09	NEF Quality Assurance Program Description (QAPD):  The licensee=s plan that defines the actions to be taken by licensee management and personnel during the performance of activities affecting quality, to ensure that quality assurance requirements are consistently met.

03.10	Operational Readiness Review (ORR):  An assessment review inspection performed by a multi disciplined inspection team to assure that a facility, or a major modification to a previously approved facility, can be operated safely within the intended safety basis.  In order to support a decision to allow operation of the facility, the NRC will review and assess the state of readiness of facility operation based on the results of the ORR inspection.  The regulations in 10 CFR 40.41(g) and 10 CFR 70.32(k) require that ANo person may commence operation of a uranium enrichment facility until the Commission verifies through inspection that the facility has been constructed in accordance with the requirements of the license.  The Commission shall publish notice of the inspection results in the Federal Register.@

03.11	Quality Assurance (QA) Program:  The licensee=s overall QA program to be applied to the design, fabrication, construction, testing, and operation of the SSCs.  This includes the NEF QAPD, QA procedures, and all supporting procedures and program activities.  The quality assurance program also provides a management control system to assure the attainment of quality objectives.

2696-04	RESPONSIBILITIES AND AUTHORITIES

04.01	Office of Nuclear Material Safety and Safeguards (NMSS)

a.	Responsible for regulatory oversight of the LES NEF.

b.	Responsible for the overall safety inspection program policy, guidance, and approval.

c.	Responsible for the planning, performance, documentation, and enforcement associated with the Headquarters criticality safety inspection program.

  - Concurs on the approval of this IMC.

04.02	 Region II Office

- Ensures that adequate resources necessary to carry out the inspection process described in this IMC are provided to the staff.

- Responsible for the planning, performance, documentation, and enforcement associated with the construction inspection program that are performed by Region II.

c.	Concurs on the approval of this IMC.

04.03	Office of Nuclear Security and Incident Response (NSIR)

a.	Responsible for policy, guidance, and approval for the physical security, classified material security, transportation security, and material control and accounting inspection programs.

b.	Responsible for the planning, performance, documentation, and enforcement associated with the Headquarters physical security, classified material security, transportation security, and material control and accounting inspection programs.  Inspection of the transportation security inspections of classified centrifuge components will be developed and coordinated by NSIR.

c.	Concurs on the approval of this IMC.

2696-05	BASIC REQUIREMENTS

05.01	General.  The NEF Construction Inspection Program provides the inspection requirements for selectively assessing the adequacy of the IROFS, and regulatory and safety-related programs.  This includes the implementation of the licensee=s QA program and other management measures used to ensure the availability and reliability of safety and safeguards IROFS.  Substantial emphasis is to be placed on the inspection of the IROFS that are most important for reducing the likelihood of high- and intermediate- consequence accidents through the implementation of commitments made by the licensee in the SAR, the Environmental Report, the NEF QAPD, and other documents that comprise the license application.  Other documents to be referenced include the SER, the ISA, the ISAS.

Emphasis is also to be placed on the licensee=s oversight that assure principal contractors who are delegated authority to conduct activities related to safety are implementing an acceptable QA program in accordance with the licensee=s QA program.  The inspection program should include direct inspections as necessary to determine whether the elements of the license=s QA program are being effectively implemented throughout all stages of construction, including equipment fabrication, assembly and installation, and structural construction activities.

05.02	Inspection Planning and Scheduling Considerations.  The NEF construction phase inspection schedule should be based on the licensee=s construction schedule and should be modified and updated periodically during the entire construction period.

Program inspections should be announced, coordinated, and scheduled with the licensee such that the efficiency and effectiveness of the inspection effort are enhanced and unnecessary burden to the licensee is minimized.  To the extent practicable, the construction and pre-operational inspections should be coordinated with the licensee to ensure that key construction activities are in accordance with the site construction project schedule.  As appropriate, inspections of various construction activities may be scheduled as unannounced inspections.

Emphasis should be placed on early identification of problems.  Inspections will be conducted periodically throughout construction.  Inspections will be scheduled early in the process during implementation of individual construction activities to develop confidence that the specific construction activities have been adequately accomplished at all stages of construction.  Comprehensive construction program reviews aimed at determining underlying causes and extent of problem areas should be conducted if NRC management concludes significant deficiencies are occurring.  Inspection depth and frequencies may be expanded to assure problem areas have been corrected.  Corrective action programs are essential to effective resolution of individual deficiencies and programmatic issues.  Inspection effort should be planned to specifically evaluate program effectiveness.

NRC Region II will develop, maintain and implement a Master Inspection Plan (MIP) and a schedule for the LES NEF construction inspection project.  The MIP will be developed in coordination with the Special Projects Branch and NSIR, and for specific time frames related to licensing or construction milestones for the project.  The MIP will include the scope and the inspection procedures that will be used for the inspections.  The list of procedures for conducting inspections is provided in Appendix A of this IMC.  The MIP will provide flexibility to address emerging issues that require additional inspection efforts, receipt of allegations, or changes in scheduling activities by the licensee.

It should be noted that the NRC has entered into a protocol agreement with the State of New Mexico=s Environmental Department (NM).  This agreement allows NM to send  state representatives to observe the NRC=s inspections at the NEF.  Effective implementation of the agreement will require advance coordination by the NRC and NM, of the inspection schedule and inspections.  It is imperative that this agreement is reviewed and understood by NRC inspectors and schedulers.

05.03	Inspection and Technical Personnel Considerations.  Qualified inspectors will be assigned responsibility for the conduct of applicable inspection requirements consistent with their experience.  In conducting this inspection program, it is necessary that inspectors be trained and/or experienced in the areas of QA, engineering, procurement, and construction activities applicable to the activities they are to inspect.  Specialists may accompany or assist inspectors to provide expertise in specific areas to enhance or expand the inspection effort.  To this aim, the inspectors may be regional, headquarters, Office of Nuclear Security and Incident Response, or the Office of Nuclear Material Safety and Safeguards inspectors.

2696-06	GUIDANCE

06.01	General.  The licensee is ultimately responsible for the safety of the nuclear facility.  The NRC ensures through a sampling type of inspection program that the responsibility is carried out in an effective manner during the activities of facility construction.  The construction inspection program presented in this manual chapter is considered the minimum necessary to achieve an acceptable level of confidence as to the adequacy of construction at the facility.

This IMC emphasizes a systematic evaluation of the adequacy and effectiveness of the licensee=s QA and construction programs and their implementation.  NRC will perform inspections of selected activities at the licensee=s project offices at the NEF site and other project facilities.  Inspections will also be performed, as necessary, at the facilities of the licensee=s consultants, contractors, and suppliers.  This IMC establishes priorities for inspection by planned sampling of IROFS and related activities consistent with their importance to safety and should consider the performance of the licensee in the areas inspected.

06.02	Program Areas.  The specific areas to be inspected will include a sampling of the licensee=s IROFS and of regulatory and safety commitments as identified in the approved SAR, ISA, ISAS, and in the latest revision of the approved NEF QAPD.  IROFS for inspection will be chosen based on safety significance and evaluated with respect to multiple safety disciplines (criticality, fire, chemical, radiological, environmental) and engineering disciplines (civil, mechanical, electrical).  The NEF=s IROFS boundary packages should be used as a resource for these inspections.

The NRC will periodically inspect the licensee=s programs for adequate assurance that IROFS are designed, procured, fabricated, and installed in accordance with the ISAS and IROFS boundary packages.  The inspections will also verify that as-built construction meets the approved design.  In addition, the licensee=s design change and design control process will be reviewed to verify that the design process effectively implements NRC requirements and other licensing design commitments made by the licensee.  These reviews may be accomplished by multi disciplinary technical review and/or inspection teams to verify the quality of design products and, inferentially, the entire facility design.  Inspections will verify that the environmental protection programs are consistent with the license application documentation (SAR, ER, etc.), the SER, the ISA, the ISAS, and design specifications and drawings.

06.03	Inspection Procedures.  The NEF CIP will use the Mixed Oxide QA and construction inspection procedures (IPs), as applicable.  These IPs are listed in Appendix A.  Some IPs may cover more than one program area and additional IPs may be used as necessary.

06.04	Implementation.  Region II is responsible for managing and implementing the inspection program described in this IMC.  The scheduling and conduct of inspections will be coordinated with Region II, the NMSS Division of Fuel Cycle Safety and Safeguards (FCSS), and NSIR, as appropriate, to ensure the effective and efficient completion of the inspection program.

This IMC is intended to provide the framework for managing the inspection effort.  Where needed, sample sizes, frequencies of periodic inspections, and the time frame when certain inspection activities are to be performed, are provided in the appropriate inspection procedure and/or inspection plan.

The inspection staff is expected to plan and conduct inspections based on safety considerations, current activities, and performance.  Region II staff should develop, on at least an annual basis, a schedule of inspections to be conducted, based on the anticipated site activities that are to be performed in the upcoming year.  Region II staff should review and revise the schedule as needed to account for changes in site activities.  The schedule will be maintained on a common drive, allowing FCSS and NSIR access to the schedule.  Any changes in the schedule directly impacting inspections coordinated with FCSS and/or NSIR personnel should be communicated to the affected individuals in as timely a manner as possible.  The activities for conducting inspections should include the following:

- Developing and documenting detailed inspection plans.

- Scheduling and coordinating inspection activities in accordance with this IMC, including coordination of inspections with the State of New Mexico=s Environmental Department (see Sections 05.02 and 06.11 for more details).

- Communicating inspection results, findings, and open items to appropriate NRC and  licensee management.

- Documenting completed inspections, findings, and open items.

Inspection issues related to occupational health and safety should be evaluated in accordance with IMC 1007, AInteraction Activities Between Regional Offices and OSHA.@

06.05	Inspection and Technical Personnel Considerations.  Inspectors and technical representatives will be assigned responsibility for performing inspections consistent with their qualifications.  In addition, inspectors performing NEF inspection activities will either be provided familiarization training on this IMC and related procedures and/or become familiar with the requirements of this IMC and the applicable requirements of 10 CFR Parts 30, 40, 70, and 95, as appropriate.

06.06	Inspection Requirements.  Inspections will be based on 10 CFR Part 30, 10 CFR Part 40, 10 CFR Part 70, and other applicable regulations, commitments, and license conditions, including the documents included as part of the license application (the SAR, etc.).  Other documents to be referenced include the applicable SER, and the ISA.  Inspections will confirm that applicable regulations, requirements, and commitments have been met.  Selection of inspection attributes will be based on safety considerations, status of work activities, and performance.

06.07	Focus of Inspections.  In order to effectively and efficiently allocate inspection resources, the NRC will perform sampling-type inspections to verify that the licensee is in compliance with NRC regulations.  A combination of IROFS sample selection, risk-based approaches, and inspections of the quality assurance program, will be used to help determine the necessary level of inspection effort.

Inspectors should use applicable risk-based information from the  license submittals, process hazard analyses, and ISA to identify those IROFS whose failure would most greatly impact the NEF=s risk profile.  This approach would allow the more risk significant IROFS to be identified so that the construction and pre-operational inspection samples could be focused on those IROFS.  The amount of inspection and activities selected for inspection should be consistent with the importance to safety of the IROFS, and the performance of the licensee in those areas.

It should be noted that a performance-based approach is more directly applicable to an operating facility and may not be readily applied to construction or pre-operational inspections.  In the early stages of the project, the majority of inspections may be compliance-based and will focus on QA program implementation.  Inspection activities should emphasize the early identification of problem areas.  It is important that inspectors evaluate whether noted problems represent isolated cases or are symptomatic of more systemic problems.  To provide the perspective to perform this evaluation, inspectors should:

  - Determine the extent and the effectiveness of licensee oversight of quality related activities.

  - Determine compliance of previously identified problem areas and/or on recurring problems.

  - Focus inspection efforts on problems that indicate programmatic weaknesses.

  - Periodically, verify the adequacy of the licensee=s corrective action program to identify, track, trend, resolve, and prevent problem recurrence.

  - Review deficiencies, audit findings, and problems identified by the licensee or by its consultants, contractors, or suppliers to identify trends and/or problem areas; and

  - Ascertain whether additional NRC inspection effort is merited in the areas of concern.

06.08	Management Entrance and Exit Meetings.  Inspectors are required to meet with licensee management as part of every inspection.  Inspectors should hold an entrance meeting with the senior licensee representative who has responsibility for the areas to be inspected.  Each inspection must include the discussion of inspection results with licensee management.  At the conclusion of an inspection, inspectors must discuss their preliminary findings with the licensee=s management at a scheduled exit meeting.  Management entrance and exit meetings with licensee personnel should be scheduled to minimize the impact on other licensee activities necessary to assure the safe and proper construction of the facility.

06.09 Inspection Reports.  Inspection findings shall be documented in inspection reports in accordance with the applicable revision to IMC 0610, ANuclear Material Safety and Safeguards Inspection Reports.@  When possible,  inspection findings should be integrated into a single inspection report to encompass findings from  in-office reviews, and/or one or more visits by regional or headquarters inspectors.  Special inspections may be documented in a separate inspection report.  Inspection issues that cannot be resolved at the time of the inspection will be documented as open items, inspection follow-up items, or unresolved items, in accordance with IMC 0610, Nuclear Material Safety and Safeguards Inspection Reports.  Region II will track open items in an inspection program information management system and subsequent inspections will include resolution of these issues.

06.10	Findings Outside of Inspector=s Qualifications.  Inspectors sometimes identify issues or violations outside of the inspector=s qualifications or expertise.  In these cases, the inspector is responsible for (1) determining if an immediate threat to the public or worker health or safety exists, and if one does exist to notify licensee management immediately; and (2) determining if the issue is better addressed by an inspector with different qualifications (i.e., a specialist inspector).  Inspectors may follow issues outside of their qualifications or expertise with the concurrence of a regional manager responsible for the area associated with the issue and the inspector=s supervisor.

06.11	Communication With Local Public Officials.  As a matter of NRC philosophy, the NRC maintains an Aopen door@ policy with regard to access by the public or federal, state and local officials to the NRC staff and to publicly available electronic documentation concerning a licensee's performance.  The degree of interaction that is considered necessary to enhance public confidence in the NRC is expected to vary widely dependant upon the situation at each facility.  Guidance pertaining to communication with stakeholders external to the NRC can be found in the latest revision of the Communication Plan for the NEF and applicable regional office procedures.  The NRC has entered into a protocol agreement with the State of New Mexico=s Environmental Department (NM).  This agreement allows NM to send  state representatives to observe the NRC=s inspections at the NEF.  Effective implementation of the agreement will require advance coordination by the NRC and NM, of the inspection schedule and inspections.  It is imperative that this agreement is reviewed and understood by NRC inspectors and schedulers.

06.12	Inspection Findings and Enforcement.  All inspection findings identified during the construction and pre-operational periods will be documented in accordance with the applicable revision to IMC 0610, ANuclear Material Safety and Safeguards Inspection Reports,@ after they have been placed in context and assessed for safety significance.  Potential violations from inspection activities will be processed in accordance with the ANRC Enforcement PolicyA (available on the NRC public web site at http://www.nrc.gov ), using traditional enforcement tools.  During construction and pre-operational activities, the guidance in Supplement II - Part 50 Facility Construction, will apply, along with other applicable supplements, for determining the appropriate severity level for quality assurance violations.  The inspection findings (or open items) will then be categorized as violations, non-cited violations, apparent violations, deviations, non-conformances, unresolved items, or inspector follow-up items.   This includes the use of notices of violations for violations of severity level IV and above and civil penalties, as appropriate.  Please note that, although IMC 0610 references IMC 0612, Power Reactor Inspection Reports, this reference is not applicable to construction projects, and IMC 0612 should not be used for determination of what constitutes a minor violation.

It is important to note that if the NRC determines that the construction is not in accordance with the licensee's commitments, then permission to operate may be denied (see 10 CFR 40.41(g), 10 CFR 70.32 (k), and NEF License Condition 11).  The failure of the licensee to meet commitments specified in the license application (including the SAR and QAPD) or other ancillary documents (the SER, ISA, ISAS), shall be documented in the inspection report(s) as noted above.  It is imperative that open items are appropriately documented in the inspection reports so that subsequent inspections can verify whether or not the licensee took the appropriate corrective actions.  The failure of the licensee to take the appropriate corrective actions to address the open items by the end of the construction phase could result in a denial by the NRC to allow operations.

06.13	Assessment of Licensee Performance (ALP).  Different types of construction activities may require certain levels of inspection effort to provide the same degree of assurance of quality work.  Increases or decreases in inspection oversight will be based on an assessment of licensee  performance.  Periodic reviews of the licensee=s performance of construction and pre-operational activities may be warranted to provide NRC management with an overview of the licensee=s performance, and provide feedback of NRC management=s conclusions regarding the quality of the licensee=s programs for protecting the public health and safety.  An objective of the program is to provide a body of information that will be used as guidance to NRC management on changes that may be required in the NEF construction and pre-operational inspection programs.  IMC 2604, ALicensee Performance Review@ describes the program for conducting and documenting evaluations of licensee performance for operating fuel cycle facilities.  Appendix B provides guidance to assess the licensee=s performance in the construction phase of the NEF.  The responsibilities and authorities, performance review scheduling, review process, and documentation guidelines, specified in IMC 2604 should be used in conducting the ALP.  Region II is responsible for adjusting the scope and frequency of the review during the construction and pre-operational phases, as needed, based on NEF construction schedules and inspection findings.  An initial recommended frequency for this assessment is once per year, with the initial assessment  occurring approximately one year after the start of construction activities.

06.14 Operational Readiness Reviews.  As stated earlier, 10 CFR 40.41(g) and 10 CFR 70.32 (k) does not allow operation of a uranium enrichment facility until the Commission verifies through inspection that the facility has been constructed in accordance with the requirements of the license.  The NRC verifies that this requirement is met by performing operational readiness reviews.  The NRC may consider the use of phased operational readiness review (ORR) inspections as a tool to provide input for NRC decisions regarding the operational readiness of NEF areas or processes.  In order to support a decision to allow operations, NRC senior management reviews and assesses the state of readiness of facility operation based on the results of the ORR inspection(s).  The status of previously identified inspection findings are also considered during the decision-making process.

END

Appendix A

LES NEF GAS CENTRIFUGE INSPECTION PROGRAM

CONSTRUCTION AND PRE-OPERATIONAL INSPECTION PROCEDURES

See IMC 2683 for a complete list of material control and accounting IPs.

Inspection procedures may be added or deleted as required.  Portions of these inspection procedures will not apply to the LES NEF.

See appropriate IMCs for a list of physical security and information security IPs.

| QA Inspection Procedures |  |
| --- | --- |
| IP 88106 | Quality Assurance: Program Development and Implementation |
| IP 88107 | Quality Assurance: Design and Documentation Control |
| IP 88108 | Quality Assurance: Control of Materials, Equipment, and Services |
| IP 88109 | Quality Assurance: Inspection, Test Control, and Control of Measuring and Test Equipment |
| IP 88110 | Quality Assurance: Problem Identification, Resolution, and Corrective Action |
| IP 88111 | 10 CFR Part 21 Inspection-Facility Construction |
| IP 88112 | Software Validation |
| IP88113 | Control of the Electronic Management of Data |
| IP 88114 | Quality Affecting Item Procurement (10 CFR Part 21) and Commercial Grade Item Dedication Process (Reactive) |
| IP 88115 | Supplier/Vendor Inspection |
| IP 88116 | Inspection of Safety Function Interfaces |
| Construction Inspection Procedures |  |
| IP 88131 | Geotechnical/Foundation Activities |
| IP 88132 | Structural Concrete |
| IP 88133 | Structural Steel and Supports |
| IP 88136 | Mechanical Components |
| IP 88137 | Electric Cable |
| IP 88138 | Electrical Components and Systems |
| IP 88139 | Ventilation and Confinement Systems |
| IP 88140 | Instrumentation and Control Systems |
| IP 55100 | Structural Welding General Inspection Procedure |
| IP 88141 | Procedures- Fire Prevention/Protection |
| IP 88142 | Underground Fire Water Loop and Equipment Installation |
| Pre-Operational Inspection Procedures |  |
| IP 83030 | Radiation Protection |
| IP 86740 | Inspection of Transportation Activities |
| IP 88005 | Management Organization and Controls |
| IP 88010 | Operator Training/Retraining |
| IP 88015 | Nuclear Criticality Safety Program |
| IP 88016 | Nuclear Criticality Evaluations and Analyses |
| IP 88017 | Criticality Alarm Systems |
| IP 88020 | Operational Safety |
| IP 88025 | Maintenance and Surveillance Testing |
| IP 88035 | Radioactive Waste Management |
| IP 88045 | Environmental Protection and Effluent Control |
| IP 88050 | Emergency Preparedness |
| IP 88051 | Evaluation of Exercises and Drills |
| IP 88055 | Fire Protection |
| IP 88056 | Process Safety Information |
| IP 88070 | Permanent Plant Modifications |
| IP 88150 | Training and Qualification of Plant Personnel |
| IP 88151 | Facility Changes and Change Process (10 CFR 70.72) |
| IP 88152 | Physical Protection Equipment and Barriers |
| IP 88153 | Material Control and Accounting |
| IP 88154 | Fire Safety and Protection Systems |
| IP 88155 | Functional Verification of IROFS |
| IP 88156 | Integrated Safety Analysis Implementation |
| IP 88157 | Waste Management Equipment and Systems |
| IP 88158 | Environmental Protection-Initial and Periodic Inspections |
| IP 88159 | Process Enclosures and Vessels |
| IP 88160 | Utilities and Bulk Chemicals |

Appendix B

LOUISIANA ENERGY SERVICES (LES) NATIONAL ENRICHMENT FACILITY (NEF)

GAS CENTRIFUGE INSPECTION PROGRAM

ASSESSMENT OF LICENSEE PERFORMANCE (ALP) PROCESS

1.		PURPOSE

This appendix provides guidance for assessing the licensee=s performance in the construction and pre-operational phases of the LES NEF gas centrifuge and to provide feedback of NRC management=s conclusions regarding the quality of the licensee=s construction and pre-operational programs.  The responsibilities and authorities, performance review scheduling, review process,  and documentation guidelines, specified in IMC 2604, Licensee Performance Review, should be used in conducting the ALP.  The results of such a review should:

1.1	Provide an assessment of licensee performance to NRC management.

1.2	Inform the licensee and the public how the NRC assesses facility performance.

1.3	Provide a basis for adjusting the construction and pre-operational inspection program, including such areas as focus, frequency, and resources.

2.		OBJECTIVES

2.1.	To describe the processes for assessing the NEF=s performance.

2.2.	To ensure that the assessments are performed in a timely, effective, and efficient manner.

2.3.	To ensure that the assessments are focused on determining whether safety has been adequately and effectively maintained.

3.		DEFINITIONS

3.1	Functional Areas: The following definitions describe the program and functional areas that form the basis for the Assessment of Licensee Performance (ALP).  It should be noted that depending on the stage of the construction project, not all functional areas would be applicable during a given assessment period.  Each functional area comprises two or more inspection program areas.

a.	Management Measures: This includes activities involving implementation of the applicable management measures as described in the licensee=s Quality Assurance Program Description and in Chapter 11 of the Safety Analysis Report.

1.	Quality Assurance: Evaluate the effectiveness of the licensee implementation of the controls as established in the NEF Quality Assurance Program Description (QAPD).

2.	Design Control: Evaluate the control of the designs for items relied on for safety (IROFS), and the control of activities associated with the preparation, review, approval, and verification of documents used for design, procurement, and fabrication.

3.	Categorization of IROFS: Evaluate the implementation of a graded quality assurance approach to the categorization of IROFS, based on safety significance, if applicable.  Note that all of the IROFS at the NEF are rated as NQA Category I, however, some of these IROFS are Asole@ IROFS.

4.	Configuration Management: Evaluate whether the licensee=s configuration management system documented an established baseline configuration; that changes to IROFS were in conformance with 10 CFR 70.72 and controlled to preclude inadvertent degradation of safety; and that a system was established and implemented to evaluate, implement, document, and track changes to the site, IROFS, processes, equipment, computer programs, and activities of personnel.

5.	Procedures: Evaluate the control of management procedures with regard to distribution, version control, management review and approval.

6.	Audits and Assessments: Evaluate the performance of audits and assessments required during construction.

7.	Records Management: Evaluate the records management system for the handling and storing of records generated or required in the design,  construction, and operation phases of the facility.

b.	Facility Construction and Pre-Operation: This includes activities involving construction and pre-operational activities.

1.	Construction Activities: Evaluate construction activities (foundation, structural concrete and steel, mechanical, electrical, and instrument components).  Evaluate whether the activities were conducted in accordance with the license application, the Safety Evaluation Report, the Integrated Safety Analysis, and the Integrated Safety Analysis Summary. Evaluate whether the licensee  recognized non routine events affecting safety, used an internal reporting system, and identified and executed corrective actions to resolve deviations from commitments made in the NEF QAPD.

2.	Pre-Operational Activities: Evaluate whether the licensee=s management measures  provided for the safe startup testing of the facility during both routine and upset conditions, recognized non routine events affecting safety, used an internal reporting system, and identified and executed corrective actions to return the facility to a safe and secure pre-operational condition after possible upsets.  Evaluate pre-operational activities, including whether the licensee has  implemented an acceptable safety operations program (including chemical safety, criticality safety, operational safety, fire protection, and radiological controls programs).

c.	Facility Support: This includes management measures and systems, including training, emergency preparedness, and maintenance.

1.	Training and Qualification of Plant Personnel: Evaluate the training and qualification of facility personnel for activities relied on for the development of safety controls; including the training, testing, retesting, and qualification of managers, designers, technical staff, construction personnel, technicians, and  other personnel whose actions are relied on for safety.

2.	Emergency Preparedness: Evaluate the effectiveness of the licensee=s emergency management program in to protect the workers, public, and the environment during reasonably postulated events that could threaten the facility.

3.	Maintenance: Evaluate the effectiveness of the licensee=s maintenance program to ensure the functionality and operability of IROFS during  reasonably postulated events that could threaten the facility and surrounding population.

d.	Safeguards and Security: Evaluate activities involving implementation of the applicable safeguards and security measures to assure adequate accounting and protection of special nuclear material during receipt and transfer operations.

e.	Special Topics:  These are issues that may arise on an occasional basis, but are not included in the review on a routine basis unless the significance of the issue rises to a level that is perceived to affect the quality of licensee performance.  Examples include the quality of application and licensing submittals, labor-management issues, and contractor difficulties.

3.2	Areas Needing Improvement:  Actual and/or potential risk-significant recurring performance (root causes or events) requiring resolution or corrective action.  If a number of deficiencies occurred early in the period and the licensee=s management corrected the problems as evidenced by no events for the last half of the cycle, then less weight should be given to those issues when evaluating the licensee=s performance.  On the other hand, more weight should be given to issues that are identified late in the assessment period.

4.		EVALUATION FACTORS

4.1	The ALP should review the licensee=s performance in each of the applicable functional areas, using a common set of evaluation criteria.  A suggested set of evaluation factors are provided below:

a.	Management involvement and control;

b.	Approach to identification and resolution of technical issues from a safety and safeguards perspective;

c.	Approach to (operational) events (including timeliness, analysis, reporting, effectiveness of corrective actions, and recognition of generic issues within the facility);

d.	Staffing (considering experience, expertise, and availability of staff and management);

e.	Aspects of performance that may reflect on the effectiveness of training and qualification programs relative to the specific functional area; and

f.	Evidence of positive or negative performance trends.

4.2	NMSS and the Region II Branch Chiefs may confer occasionally to consider the suitability of the current evaluation factors and recommend any necessary changes.

- IMPLEMENTATION

5.1	The responsibilities and authorities, performance review scheduling, review process,  and documentation guidelines, specified in IMC 2604, Licensee Performance Review, should be used in conducting the ALP.

Attachment 1

Revision History of IMC 2696

| Commitment Tracking Number | Issue Date | Description of Change | Training Required | Training Completion Date | Comment Resolution Accession Number |
| --- | --- | --- | --- | --- | --- |
| N/A | 10/19/06 CN 06-028 | Document created to implement the construction and operational readiness review inspection program at LES NEF | None | N/A | ML062620225 |