## Export
This data is updated occasionally - last updated on 03/20/2024.
ID | Task | Status | Type of Review | Start | End | Duration (days) | No. Milestones Completed | Total Milestones | Pct Complete
1.0 | Application Acceptance | Completed | Safety and Safeguards | 2022-09-23 | 2022-11-18 | 56 | 7 | 7 | 100%
1.1 | Hearing Request | Completed | Safety and Safeguards | 2023-02-03 | 2023-04-04 | 60 | 4 | 4 | 100%
1.2 | Initial Draft SER | In progress | Safety and Safeguards | 2022-12-01 | 2024-02-23 | 449 | 11 | 20 | 55%
1.3 | Issue RAIs | In progress | Safety and Safeguards | 2022-12-01 | 2024-02-23 | 449 | 15 | 20 | 75%
1.4 | Resolve RAIs | In progress | Safety and Safeguards | 2022-12-01 | 2024-05-31 | 547 | 15 | 20 | 75%
1.5 | Final Draft SER | Pending | Safety and Safeguards | 2024-01-01 | 2024-09-30 | 273 | 0 | 20 | 0%
1.6 | Concurrence on Final Draft SER | Pending | Safety and Safeguards | 2024-09-30 | 2024-12-31 | 92 | 0 | 5 | 0%
1.7 | ACRS Review | Pending | Safety and Safeguards | 2025-01-13 | 2025-05-30 | 137 | 0 | 5 | 0%
1.8 | Complete SER and Licensing Decision | Pending | Safety and Safeguards | 2025-05-31 | 2025-06-30 | 30 | 0 | 5 | 0%
2.0 | ER Acceptance | Completed | Environmental Impact | 2022-09-23 | 2022-11-18 | 56 | 4 | 4 | 100%
2.1 | Scoping | In progress | Environmental Impact | 2022-08-31 | 2022-12-30 | 121 | 5 | 5 | 100%
2.2 | Draft EIS | In progress | Environmental Impact | 2023-03-01 | 2024-02-28 | 364 | 4 | 9 | 44.44%
2.3 | Draft EIS Comment Period | Pending | Environmental Impact | 2024-03-01 | 2024-05-01 | 61 | 0 | 6 | 0%
2.4 | Final EIS | Pending | Environmental Impact | 2024-05-01 | 2025-03-31 | 334 | 0 | 4 | 0%
2.5 | EPA Notification | Pending | Environmental Impact | 2025-04-01 | 2025-05-01 | 30 | 0 | 2 | 0%
3.0 | Readiness Review | Pending | Readiness Review | 2025-10-01 | 2026-03-31 | 181 | 0 | 3 | 0%